## README
TPRM-008 ¦ Vendor Risk Assessment Register | Mayekar Technologies Pvt. Ltd.
Purpose | Detailed third-party risk assessment covering inherent risk, control effectiveness, residual risk and treatment.
Version | 1.0
Prepared By | Omkar Abhay Mayekar
Status | Portfolio / Simulated Evidence
Method | Likelihood × Impact, 1–5 scale
Rating | 1–4 Low ¦ 5–9 Medium ¦ 10–16 High ¦ 17–25 Critical
Disclaimer | All vendors, evidence and assessments are simulated for portfolio/learning purposes and are not actual client evidence.

## Vendor Risk Assessment
TPRM-008 ¦ VENDOR RISK ASSESSMENT REGISTER
Mayekar Technologies Pvt. Ltd. ¦ ISO/IEC 27001:2022-aligned simulated portfolio evidence
Risk ID | Vendor ID | Vendor Name | Risk Scenario | Asset / Information | Threat | Vulnerability | Existing Controls | Likelihood | Impact | Inherent Risk Score | Inherent Risk Rating | Control Effectiveness | Residual Likelihood | Residual Impact | Residual Risk Score | Residual Risk Rating | Risk Treatment | Treatment Action | Risk Owner | Target Date | Risk Status | Evidence / Reference | Risk Category | Acceptance Required | Escalation Required | Review Frequency
TPRM-RISK-001 | VND-001 | CloudSphere Infrastructure | Unauthorized access or compromise of production cloud infrastructure could result in data breach, service disruption, or loss of critical business services. | Production cloud infrastructure; customer data; source code; business data | External cyber attack; credential compromise; ransomware; cloud account takeover | Privileged remote access; complex cloud environment; excessive permissions; configuration errors | MFA; privileged access management; encryption; network segmentation; logging and monitoring; vulnerability management; backup and recovery controls | 4 | 5 | 20 | Critical | Strong | 2 | 5 | 10 | High | Mitigate | Review privileged cloud access; enforce MFA and PAM; validate network segmentation; perform configuration review; obtain updated security assurance evidence. | IT Security Manager | 2026-09-30 | Open | Vendor security questionnaire; ISO 27001 certificate; SOC report; cloud security assessment; access review evidence | Access Control | No | Yes | 6 Months
TPRM-RISK-002 | VND-002 | Microsoft 365 Services | Compromise of corporate email or collaboration services could result in unauthorized disclosure, phishing, account takeover, or business email compromise. | Microsoft 365 tenant; corporate email; employee data; customer and business information | Phishing; credential theft; account takeover; malicious insider | Phishing exposure; account compromise; broad user access; misconfigured sharing | MFA; conditional access; encryption; audit logging; DLP; endpoint protection; access reviews | 3 | 4 | 12 | High | Strong | 2 | 4 | 8 | Medium | Mitigate | Review conditional access and MFA configuration; validate DLP and sharing controls; perform access review; obtain updated security assurance evidence. | IT Security Manager | 2026-09-30 | Open | Vendor security questionnaire; ISO 27001 certificate; SOC report; conditional access configuration; access review evidence | Access Control | No | No | 12 Months
TPRM-RISK-003 | VND-003 | SecureVault Backup | Failure or compromise of backup services could result in loss, corruption, or unavailability of business-critical recovery data. | Cloud backup repository; backup data; recovery information | Ransomware; backup compromise; accidental deletion; unauthorized access | Insufficient backup isolation; excessive administrative access; inadequate recovery testing | Encryption; backup retention; access control; backup monitoring; recovery procedures; MFA | 3 | 5 | 15 | High | Strong | 2 | 5 | 10 | High | Mitigate | Validate backup isolation; test restoration; review administrative access; confirm encryption and retention controls. | IT Operations Manager | 2026-09-30 | Open | Vendor security questionnaire; backup configuration; restoration test report; encryption evidence; access review | Availability / BCP | No | Yes | 6 Months
TPRM-RISK-004 | VND-004 | TalentCore HRMS | Unauthorized access to the HR platform could expose employee personal information and sensitive HR records. | HRMS platform; employee records; HR information | Credential theft; insider misuse; unauthorized access; phishing | Weak access controls; excessive user permissions; inadequate periodic access review | MFA; role-based access; access reviews; encryption; audit logging; HR data protection | 3 | 4 | 12 | High | Moderate | 2 | 4 | 8 | Medium | Mitigate | Review HRMS role assignments; enforce MFA; perform access review; validate employee data protection and incident response controls. | HR Manager | 2026-10-15 | Open | Vendor security questionnaire; HRMS security documentation; access review; data protection evidence | Access Control | No | No | 12 Months
TPRM-RISK-005 | VND-005 | PayMatrix Solutions | Payroll system compromise could expose employee financial information or cause inaccurate or delayed salary processing. | Payroll platform; employee financial data; payroll records | Credential compromise; financial fraud; insider misuse; system attack | Sensitive financial data exposure; weak authentication; inadequate segregation of duties | MFA; role-based access; encryption; segregation of duties; transaction monitoring; audit logging | 3 | 4 | 12 | High | Moderate | 2 | 4 | 8 | Medium | Mitigate | Review payroll access and segregation of duties; validate MFA and encryption; perform security assessment; confirm incident response capability. | Finance Manager | 2026-10-15 | Open | Vendor security questionnaire; payroll security documentation; access review; segregation of duties evidence | Data Protection | No | No | 12 Months
TPRM-RISK-006 | VND-006 | SalesFlow CRM | Unauthorized access to the CRM could expose customer information and disrupt sales operations. | CRM platform; customer records; sales data | Account takeover; data exfiltration; insider misuse; malware | Excessive user permissions; compromised credentials; inadequate access review | MFA; role-based access; encryption; audit logging; periodic access reviews | 3 | 4 | 12 | High | Moderate | 2 | 4 | 8 | Medium | Mitigate | Review CRM access permissions; validate MFA and encryption; perform periodic access review; confirm incident response controls. | Sales Operations Manager | 2026-10-15 | Open | Vendor security questionnaire; CRM security documentation; access review; encryption evidence | Access Control | No | No | 12 Months
TPRM-RISK-007 | VND-007 | NetShield SOC Services | Compromise of the managed SOC provider could reduce security monitoring capability and delay detection or response to incidents. | SOC monitoring platform; security logs; alerts; incident information | Compromise of security monitoring provider; insider threat; service disruption | Provider dependency; privileged access; inadequate segregation of duties; monitoring gaps | MFA; privileged access management; 24x7 monitoring; incident response; security logging; access reviews | 3 | 5 | 15 | High | Strong | 2 | 5 | 10 | High | Mitigate | Perform enhanced provider assessment; review privileged access; validate monitoring and incident response controls; establish escalation and assurance requirements. | Security Operations Manager | 2026-09-30 | Open | Vendor security questionnaire; SOC report; privileged access review; incident response documentation | Cybersecurity | No | Yes | 6 Months
TPRM-RISK-008 | VND-008 | RedFort Security Testing | Unauthorized disclosure or misuse of security testing information could expose system vulnerabilities and sensitive security findings. | Security testing platform; vulnerability reports; penetration testing results | Unauthorized disclosure; insider misuse; exploitation of testing environment | Sensitive security findings; controlled testing environment exposure; inadequate data protection | Controlled testing environment; confidentiality agreements; access restrictions; secure file transfer; evidence handling procedures | 3 | 4 | 12 | High | Strong | 2 | 4 | 8 | Medium | Mitigate | Validate secure testing environment; review evidence handling; restrict access to security findings; confirm confidentiality requirements. | Application Security Manager | 2026-10-15 | Open | Vendor security questionnaire; penetration testing methodology; testing environment controls; confidentiality agreement | Data Protection | No | No | 12 Months
TPRM-RISK-009 | VND-009 | EndpointGuard Technologies | Compromise of endpoint security infrastructure could allow attackers to disable security controls or gain administrative access to endpoints. | Endpoint security platform; endpoint telemetry; security configurations | Malware; credential compromise; security control tampering; insider misuse | Privileged endpoint administration; excessive permissions; delayed security updates | MFA; EDR; privileged access management; endpoint monitoring; vulnerability management; security logging | 3 | 5 | 15 | High | Strong | 2 | 5 | 10 | High | Mitigate | Review endpoint administrative access; validate PAM and MFA; confirm EDR protection; perform privileged access review. | IT Security Manager | 2026-09-30 | Open | Vendor security questionnaire; ISO 27001 certificate; SOC report; EDR configuration; privileged access review | Access Control | No | Yes | 6 Months
TPRM-RISK-010 | VND-010 | ConnectNet Communications | Network service disruption or compromise could affect internet connectivity and business communications. | Corporate network; network connectivity; network metadata | DDoS; network attack; infrastructure failure; ISP compromise | Single network provider dependency; insufficient redundancy; inadequate monitoring | Network monitoring; firewall; redundancy; DDoS protection; incident response; availability monitoring | 3 | 4 | 12 | High | Moderate | 2 | 4 | 8 | Medium | Mitigate | Validate network redundancy; review DDoS protection and monitoring; confirm incident response and availability controls. | Network Operations Manager | 2026-10-15 | Open | Vendor security questionnaire; network security documentation; availability monitoring; incident response records | Cybersecurity | No | No | 12 Months
TPRM-RISK-011 | VND-011 | DataCenterOne | Data center outage, physical incident, or unauthorized infrastructure access could disrupt critical hosted services. | Data center infrastructure; hosted systems; business data | Ransomware; physical disruption; unauthorized access; infrastructure failure | Physical infrastructure dependency; privileged administrative access; limited alternate capacity | Physical security; CCTV; access control; environmental monitoring; redundancy; backup power; infrastructure monitoring | 3 | 5 | 15 | High | Strong | 2 | 5 | 10 | High | Mitigate | Review physical and logical access; validate redundancy and recovery capability; obtain updated assurance evidence; confirm subcontractor controls. | IT Infrastructure Manager | 2026-09-30 | Open | Vendor security questionnaire; ISO 27001 certificate; SOC report; physical security evidence; DR documentation | Availability / BCP | No | Yes | 6 Months
TPRM-RISK-012 | VND-012 | RecruitPro Services | Unauthorized disclosure of candidate information could result in privacy violations or misuse of recruitment data. | Recruitment platform; candidate records; recruitment information | Phishing; unauthorized disclosure; insider misuse; data theft | Third-party access to candidate information; excessive data retention; inadequate access review | Access controls; confidentiality agreements; data protection requirements; background verification | 3 | 3 | 9 | Medium | Moderate | 2 | 3 | 6 | Medium | Mitigate | Review candidate data access and retention; perform access review; validate privacy and confidentiality controls. | HR Manager | 2026-11-30 | Open | Vendor security questionnaire; data protection documentation; access review; confidentiality agreement | Data Protection | No | No | 12 Months
TPRM-RISK-013 | VND-013 | FinLedger Systems | Compromise of the financial platform could expose financial records or affect accounting accuracy and reporting. | Financial platform; accounting records; financial information | Financial fraud; ransomware; unauthorized access; data manipulation | Sensitive financial records; excessive privileges; inadequate segregation of duties | MFA; role-based access; segregation of duties; encryption; audit logging; financial controls | 3 | 4 | 12 | High | Strong | 2 | 4 | 8 | Medium | Mitigate | Review financial system privileges; validate segregation of duties and MFA; perform security assessment; confirm audit logging. | Finance Manager | 2026-10-15 | Open | Vendor security questionnaire; ISO 27001 certificate; SOC report; financial controls; access review | Access Control | No | No | 12 Months
TPRM-RISK-014 | VND-014 | PayGate Services | Payment processing failure or compromise could result in transaction disruption, financial loss, or customer data exposure. | Payment gateway; customer transaction data; payment information | Payment fraud; cyber attack; service disruption; data breach | High-value transaction processing; integration dependency; authentication weaknesses | MFA; encryption; transaction monitoring; fraud detection; network security; incident response | 3 | 5 | 15 | High | Strong | 2 | 5 | 10 | High | Mitigate | Perform enhanced payment security assessment; validate MFA, encryption, fraud monitoring and incident response; review regulatory requirements. | Finance Manager | 2026-09-30 | Open | Vendor security questionnaire; ISO 27001 certificate; SOC report; payment security documentation; transaction monitoring evidence | Data Protection | No | Yes | 6 Months
TPRM-RISK-015 | VND-015 | ServiceDesk Pro | Compromise of IT support services could provide unauthorized remote administrative access to internal systems. | IT service management platform; support records; administrative access | Credential theft; insider misuse; unauthorized remote access | Remote administrative access; excessive privileges; insufficient session monitoring | MFA; privileged access management; remote access controls; session logging; ticket-based access | 4 | 4 | 16 | High | Moderate | 3 | 4 | 12 | High | Mitigate | Review remote administrative access; enforce PAM and MFA; validate session monitoring; perform privileged access review. | IT Operations Manager | 2026-09-30 | Open | Vendor security questionnaire; privileged access review; MFA configuration; remote access logs | Access Control | No | Yes | 6 Months
TPRM-RISK-016 | VND-016 | PrintSecure Solutions | Unauthorized access to printed confidential documents could result in information disclosure. | Managed print system; printed business documents | Unauthorized physical access; document theft; accidental disclosure | Physical document handling; human error; inadequate secure printing controls | Access control; secure printing; document handling procedures; confidentiality requirements | 2 | 2 | 4 | Low | Strong | 1 | 2 | 2 | Low | Accept | Continue existing controls; periodically verify secure printing and document handling requirements. | Administration Manager | 2026-12-31 | Accepted | Secure printing procedure; confidentiality requirements; document handling records | Access Control | Yes | No | 24 Months
TPRM-RISK-017 | VND-017 | DocuSign Services | Compromise of electronic signature services could affect contractual integrity or unauthorized document execution. | Electronic signature platform; signed documents; contracts | Account takeover; unauthorized document execution; insider misuse | Cloud service dependency; account compromise; inadequate access review | MFA; encryption; audit logging; access reviews; digital signature controls | 3 | 3 | 9 | Medium | Strong | 2 | 3 | 6 | Medium | Mitigate | Review access permissions and MFA; validate electronic signature integrity and audit logging. | Legal & Compliance Manager | 2026-11-30 | Open | Vendor security questionnaire; ISO 27001 certificate; access review; audit logs | Cybersecurity | No | No | 12 Months
TPRM-RISK-018 | VND-018 | LegalEdge Associates | Unauthorized disclosure of confidential legal documents could create legal, contractual, or confidentiality risks. | Legal document management; contracts; legal records | Unauthorized disclosure; insider misuse; cyber attack | Confidential legal information; third-party access; inadequate information segregation | Confidentiality agreements; access control; document management; secure communication | 2 | 4 | 8 | Medium | Moderate | 1 | 4 | 4 | Low | Accept | Maintain confidentiality and access controls; review handling of confidential legal records periodically. | Legal & Compliance Manager | 2026-12-31 | Accepted | Confidentiality agreement; legal service security requirements; access review | Data Protection | Yes | No | 24 Months
TPRM-RISK-019 | VND-019 | ComplianceCheck Advisory | Inadequate protection of compliance information could result in unauthorized disclosure or inaccurate compliance reporting. | GRC compliance platform; compliance records; security information | Unauthorized access; data leakage; insider misuse | Sensitive compliance information; excessive user access; inadequate data classification | Access control; data classification; confidentiality requirements; audit logging | 2 | 3 | 6 | Medium | Moderate | 1 | 3 | 3 | Low | Accept | Review user access and data classification; validate compliance information protection and monitoring. | GRC Manager | 2026-12-31 | Accepted | Vendor security questionnaire; compliance assessment; access review; data classification records | Data Protection | Yes | No | 24 Months
TPRM-RISK-020 | VND-020 | SecureShred Services | Improper destruction or handling of confidential documents could result in information leakage. | Confidential documents; disposal records; storage media | Unauthorized disposal; theft; accidental disclosure; insider misuse | Human handling of confidential material; inadequate chain of custody; incomplete destruction verification | Secure disposal procedures; chain-of-custody records; destruction certificates | 2 | 3 | 6 | Medium | Strong | 1 | 3 | 3 | Low | Accept | Maintain secure disposal controls; verify chain-of-custody and destruction evidence. | Administration Manager | 2026-12-31 | Accepted | Secure disposal procedure; chain-of-custody records; destruction certificate | Data Protection | Yes | No | 24 Months
TPRM-RISK-021 | VND-021 | GuardForce Security | Unauthorized physical access could compromise facilities, personnel safety, or protected areas. | Physical security facilities; employee and visitor information | Unauthorized physical access; theft; sabotage | Third-party physical access; inadequate access review; human error | Physical access controls; visitor management; security guards; background checks | 2 | 3 | 6 | Medium | Moderate | 1 | 3 | 3 | Low | Accept | Review physical access authorization; validate personnel security and visitor management. | Facilities Manager | 2026-12-31 | Accepted | Physical security procedure; visitor management records; personnel security evidence | Access Control | Yes | No | 24 Months
TPRM-RISK-022 | VND-022 | SafeCam Systems | Unauthorized access to CCTV systems could expose surveillance information or enable tampering with security monitoring. | CCTV surveillance platform; video surveillance recordings | Unauthorized access; surveillance tampering; data leakage | Physical access to surveillance systems; weak administrator controls; inadequate retention controls | Access control; CCTV security controls; administrator authentication; monitoring | 2 | 3 | 6 | Medium | Moderate | 1 | 3 | 3 | Low | Accept | Review CCTV administrator access and retention controls; validate privacy and monitoring safeguards. | Facilities Manager | 2026-12-31 | Accepted | CCTV security configuration; administrator access review; retention controls | Access Control | Yes | No | 24 Months
TPRM-RISK-023 | VND-023 | OfficeNet Infrastructure | Compromise of network maintenance services could provide unauthorized access to network infrastructure or configuration information. | Network infrastructure; configurations; network devices | Network intrusion; configuration manipulation; insider misuse | Privileged network access; configuration errors; inadequate change control | Privileged access management; network segmentation; change management; configuration backups | 3 | 4 | 12 | High | Moderate | 2 | 4 | 8 | Medium | Mitigate | Review privileged network access; validate change management and configuration controls; perform technical access review. | Network Operations Manager | 2026-10-15 | Open | Network security assessment; privileged access review; change management records | Access Control | No | No | 12 Months
TPRM-RISK-024 | VND-024 | CodeSecure Labs | Unauthorized access to source code or security testing results could expose application vulnerabilities. | Application source code; security assessment reports; vulnerability findings | Source code theft; unauthorized access; exploitation | Source code access; privileged testing access; inadequate environment segregation | Controlled testing environments; source code access controls; confidentiality agreements; vulnerability management | 3 | 4 | 12 | High | Strong | 2 | 4 | 8 | Medium | Mitigate | Review source code access; validate segregation of testing environments; confirm vulnerability management and confidentiality controls. | Application Security Manager | 2026-10-15 | Open | Application security assessment; source code access controls; testing environment evidence | Access Control | No | No | 12 Months
TPRM-RISK-025 | VND-025 | LearnSecure Training | Inadequate protection of training records could expose limited employee information or reduce security awareness effectiveness. | Training platform; employee training records | Credential compromise; unauthorized access; insider misuse | Employee information exposure; shared access; inadequate access review | MFA; role-based access; training records access controls; confidentiality requirements | 2 | 2 | 4 | Low | Moderate | 1 | 2 | 2 | Low | Accept | Maintain existing controls; periodically review training platform access and employee data handling. | HR Manager | 2026-12-31 | Accepted | Security awareness procedure; training records; access controls | Data Protection | Yes | No | 24 Months
TPRM-RISK-026 | VND-026 | TeleSupport Services | Compromise of customer support services could expose customer information or disrupt customer-facing operations. | Customer support platform; customer records; support tickets | Account takeover; data exfiltration; service disruption | Remote customer data access; excessive permissions; inadequate monitoring | MFA; role-based access; call monitoring; audit logging; data protection controls | 3 | 4 | 12 | High | Moderate | 2 | 4 | 8 | Medium | Mitigate | Review customer support access; enforce MFA and role-based access; validate monitoring and data protection. | Customer Operations Manager | 2026-10-15 | Open | Vendor security questionnaire; access review; customer data protection evidence | Data Protection | No | No | 12 Months
TPRM-RISK-027 | VND-027 | MarketReach Analytics | Unauthorized access to marketing analytics could expose customer insights or business-sensitive marketing information. | Marketing analytics platform; customer analytics; marketing information | Unauthorized access; data leakage; insider misuse | Customer analytics exposure; excessive data access; insufficient data minimization | Role-based access; data minimization; encryption; access reviews | 2 | 3 | 6 | Medium | Moderate | 1 | 3 | 3 | Low | Accept | Review analytics access and data minimization; validate encryption and periodic access reviews. | Marketing Manager | 2026-12-31 | Accepted | Vendor security questionnaire; data protection controls; access review; analytics security documentation | Access Control | Yes | No | 24 Months
TPRM-RISK-028 | VND-028 | DevCloud Platform | Compromise of the development cloud platform could expose source code, credentials, or development environments. | Development cloud platform; source code; development environments | Source code theft; credential compromise; malware; unauthorized access | Developer privileged access; exposed credentials; inadequate environment segregation | MFA; privileged developer access; source code controls; repository security; logging and monitoring | 3 | 4 | 12 | High | Strong | 2 | 4 | 8 | Medium | Mitigate | Review privileged developer access; validate source code protection, MFA and environment segregation. | Engineering Manager | 2026-10-15 | Open | Vendor security questionnaire; ISO 27001 certificate; source code protection; privileged access review | Access Control | No | No | 12 Months
TPRM-RISK-029 | VND-029 | DisasterReady DR Services | Failure of disaster recovery services could prevent timely recovery of critical business operations after a major disruption. | Disaster recovery platform; backup and recovery infrastructure | Ransomware; infrastructure failure; service provider outage | Recovery infrastructure dependency; insufficient recovery testing; configuration errors | Redundant recovery infrastructure; backup controls; recovery procedures; DR testing | 3 | 5 | 15 | High | Strong | 2 | 5 | 10 | High | Mitigate | Perform DR capability assessment; test recovery procedures; validate redundancy and recovery objectives. | IT Operations Manager | 2026-09-30 | Open | Vendor security questionnaire; ISO 27001 certificate; SOC report; DR test report; recovery documentation | Availability / BCP | No | Yes | 6 Months
TPRM-RISK-030 | VND-030 | SecureCourier Logistics | Loss, theft, or unauthorized access to confidential documents during transportation could result in information disclosure. | Confidential documents; shipment records; delivery information | Document theft; loss during transit; unauthorized access | Human handling during transportation; theft or loss; inadequate chain of custody | Chain-of-custody procedures; secure packaging; delivery tracking; confidentiality requirements | 2 | 2 | 4 | Low | Strong | 1 | 2 | 2 | Low | Accept | Maintain chain-of-custody controls; periodically verify secure packaging, tracking and confidentiality requirements. | Administration Manager | 2026-12-31 | Accepted | Chain-of-custody records; secure transportation procedure; delivery tracking evidence | Access Control | Yes | No | 24 Months

## Executive Summary
TPRM-008 ¦ EXECUTIVE RISK SUMMARY
Metric | Value | Management Interpretation | Residual Risk | Count
Total Risk Assessments | 30 | 30 vendor-level assessments | Low | 9
Critical Inherent Risks | 1 | Immediate management attention | Medium | 13
High Inherent Risks | 18 | Active treatment required | High | 8
High Residual Risks | 8 | Escalation / monitoring required | Critical | 0
Medium Residual Risks | 13 | Track treatment
Low Residual Risks | 9 | Routine monitoring
Mitigation Actions | 21 | Open treatment population
Accepted Risks | 9 | Formal acceptance should be documented
Strong Controls | 16 | Controls substantially reduce exposure
Moderate Controls | 14 | Controls partially reduce exposure

## Risk Heatmap
Impact \ Likelihood | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25
4 | 4 | 8 | 12 | 16 | 20
3 | 3 | 6 | 9 | 12 | 15
2 | 2 | 4 | 6 | 8 | 10
1 | 1 | 2 | 3 | 4 | 5
Rating Bands | 1–4 Low ¦ 5–9 Medium ¦ 10–16 High ¦ 17–25 Critical
Method | Risk Score = Likelihood × Impact

## Action Tracker
Action ID | Risk ID | Vendor | Residual Risk | Treatment | Priority | Action Owner | Target Date | Status | Verification Evidence | Escalation
ACT-001 | TPRM-RISK-001 | CloudSphere Infrastructure | High | Mitigate | High | IT Security Manager | 2026-09-30 | Open | To be attached after remediation verification | Yes
ACT-002 | TPRM-RISK-002 | Microsoft 365 Services | Medium | Mitigate | Medium | IT Security Manager | 2026-09-30 | Open | To be attached after remediation verification | No
ACT-003 | TPRM-RISK-003 | SecureVault Backup | High | Mitigate | High | IT Operations Manager | 2026-09-30 | Open | To be attached after remediation verification | Yes
ACT-004 | TPRM-RISK-004 | TalentCore HRMS | Medium | Mitigate | Medium | HR Manager | 2026-10-15 | Open | To be attached after remediation verification | No
ACT-005 | TPRM-RISK-005 | PayMatrix Solutions | Medium | Mitigate | Medium | Finance Manager | 2026-10-15 | Open | To be attached after remediation verification | No
ACT-006 | TPRM-RISK-006 | SalesFlow CRM | Medium | Mitigate | Medium | Sales Operations Manager | 2026-10-15 | Open | To be attached after remediation verification | No
ACT-007 | TPRM-RISK-007 | NetShield SOC Services | High | Mitigate | High | Security Operations Manager | 2026-09-30 | Open | To be attached after remediation verification | Yes
ACT-008 | TPRM-RISK-008 | RedFort Security Testing | Medium | Mitigate | Medium | Application Security Manager | 2026-10-15 | Open | To be attached after remediation verification | No
ACT-009 | TPRM-RISK-009 | EndpointGuard Technologies | High | Mitigate | High | IT Security Manager | 2026-09-30 | Open | To be attached after remediation verification | Yes
ACT-010 | TPRM-RISK-010 | ConnectNet Communications | Medium | Mitigate | Medium | Network Operations Manager | 2026-10-15 | Open | To be attached after remediation verification | No
ACT-011 | TPRM-RISK-011 | DataCenterOne | High | Mitigate | High | IT Infrastructure Manager | 2026-09-30 | Open | To be attached after remediation verification | Yes
ACT-012 | TPRM-RISK-012 | RecruitPro Services | Medium | Mitigate | Medium | HR Manager | 2026-11-30 | Open | To be attached after remediation verification | No
ACT-013 | TPRM-RISK-013 | FinLedger Systems | Medium | Mitigate | Medium | Finance Manager | 2026-10-15 | Open | To be attached after remediation verification | No
ACT-014 | TPRM-RISK-014 | PayGate Services | High | Mitigate | High | Finance Manager | 2026-09-30 | Open | To be attached after remediation verification | Yes
ACT-015 | TPRM-RISK-015 | ServiceDesk Pro | High | Mitigate | High | IT Operations Manager | 2026-09-30 | Open | To be attached after remediation verification | Yes
ACT-016 | TPRM-RISK-016 | PrintSecure Solutions | Low | Accept | Low | Administration Manager | 2026-12-31 | Open | To be attached after remediation verification | No
ACT-017 | TPRM-RISK-017 | DocuSign Services | Medium | Mitigate | Medium | Legal & Compliance Manager | 2026-11-30 | Open | To be attached after remediation verification | No
ACT-018 | TPRM-RISK-018 | LegalEdge Associates | Low | Accept | Low | Legal & Compliance Manager | 2026-12-31 | Open | To be attached after remediation verification | No
ACT-019 | TPRM-RISK-019 | ComplianceCheck Advisory | Low | Accept | Low | GRC Manager | 2026-12-31 | Open | To be attached after remediation verification | No
ACT-020 | TPRM-RISK-020 | SecureShred Services | Low | Accept | Low | Administration Manager | 2026-12-31 | Open | To be attached after remediation verification | No
ACT-021 | TPRM-RISK-021 | GuardForce Security | Low | Accept | Low | Facilities Manager | 2026-12-31 | Open | To be attached after remediation verification | No
ACT-022 | TPRM-RISK-022 | SafeCam Systems | Low | Accept | Low | Facilities Manager | 2026-12-31 | Open | To be attached after remediation verification | No
ACT-023 | TPRM-RISK-023 | OfficeNet Infrastructure | Medium | Mitigate | Medium | Network Operations Manager | 2026-10-15 | Open | To be attached after remediation verification | No
ACT-024 | TPRM-RISK-024 | CodeSecure Labs | Medium | Mitigate | Medium | Application Security Manager | 2026-10-15 | Open | To be attached after remediation verification | No
ACT-025 | TPRM-RISK-025 | LearnSecure Training | Low | Accept | Low | HR Manager | 2026-12-31 | Open | To be attached after remediation verification | No
ACT-026 | TPRM-RISK-026 | TeleSupport Services | Medium | Mitigate | Medium | Customer Operations Manager | 2026-10-15 | Open | To be attached after remediation verification | No
ACT-027 | TPRM-RISK-027 | MarketReach Analytics | Low | Accept | Low | Marketing Manager | 2026-12-31 | Open | To be attached after remediation verification | No
ACT-028 | TPRM-RISK-028 | DevCloud Platform | Medium | Mitigate | Medium | Engineering Manager | 2026-10-15 | Open | To be attached after remediation verification | No
ACT-029 | TPRM-RISK-029 | DisasterReady DR Services | High | Mitigate | High | IT Operations Manager | 2026-09-30 | Open | To be attached after remediation verification | Yes
ACT-030 | TPRM-RISK-030 | SecureCourier Logistics | Low | Accept | Low | Administration Manager | 2026-12-31 | Open | To be attached after remediation verification | No

## Methodology
Control Area | Definition | Portfolio Rule
Likelihood | Probability/frequency of risk occurrence | 1 Rare ¦ 2 Unlikely ¦ 3 Possible ¦ 4 Likely ¦ 5 Almost Certain
Impact | Business, information, financial, legal, customer and availability consequence | 1 Insignificant ¦ 2 Minor ¦ 3 Moderate ¦ 4 Major ¦ 5 Severe
Inherent Risk | Risk before considering existing controls | Likelihood × Impact
Residual Risk | Risk remaining after existing controls | Residual Likelihood × Residual Impact
Strong Control Effectiveness | Controls substantially reduce risk exposure | Documented, implemented and periodically reviewed controls
Moderate Control Effectiveness | Controls partially reduce risk exposure | Controls exist but improvement/assurance is needed
Weak Control Effectiveness | Material control gaps remain | Treatment should be prioritized
Accept | Risk is within approved tolerance | Document rationale and approval
Mitigate | Additional controls/actions reduce risk | Track action through verification and closure
Transfer | Risk is contractually/financially transferred | Verify contractual mechanism and limitations
Avoid | Activity/service is stopped or not undertaken | Document business decision
Review Trigger | Event requiring reassessment | Material service change, incident, control failure, contract change or scheduled review
Evidence Rule | Assessment conclusions should be traceable | Link questionnaire, certifications, SOC reports, tests, contracts and review evidence

## Document Control
Field | Value
Document Title | Vendor Risk Assessment Register
Document ID | MTPL-TPRM-008
Version | 1.0
Organization | Mayekar Technologies Pvt. Ltd.
Prepared By | Omkar Abhay Mayekar
Reviewed By | GRC Manager — Simulated
Approved By | Management — Simulated
Effective Date | 2026-08-01
Review Cycle | Annual or upon material change
Classification | Internal / Confidential
Status | Portfolio / Simulated
Scope | Third-party vendor risk assessments supporting the organization's information security and business operations.
Disclaimer | All vendors, evidence and assessment results are simulated for learning/portfolio purposes.