## README
TPRM-024 ¦ VENDOR RISK ACCEPTANCE & RESIDUAL RISK REGISTER | Mayekar Technologies Pvt. Ltd.
Document ID | MTPL-TPRM-024
Version | 1.0
Prepared By | Omkar Abhay Mayekar
Status | Portfolio / Simulated Evidence
Purpose | Formal register for documenting residual risk after vendor controls/treatment, risk acceptance rationale, accountable ownership, approval authority, conditions, review dates and expiry.
Acceptance Principle | Risk acceptance is a governance decision to retain residual risk within approved tolerance; it does not eliminate the risk or replace remediation where remediation remains required.
Required Inputs | Current risk assessment, treatment status, residual risk, exceptions/waivers, business impact, compensating controls and management risk appetite/tolerance.
Review Principle | Accepted risks must be periodically reviewed and reassessed when material changes, incidents, control failures or expiry conditions occur.
Disclaimer | All risk acceptance records, ratings, rationale, approvals and dates are simulated for portfolio/learning purposes.

## Document Control
Field | Value
Document Title | Vendor Risk Acceptance & Residual Risk Register
Document ID | MTPL-TPRM-024
Version | 1.0
Organization | Mayekar Technologies Pvt. Ltd.
Prepared By | Omkar Abhay Mayekar
Reviewed By | GRC Manager — Simulated
Approved By | Management — Simulated
Effective Date | 2026-08-01
Review Cycle | Quarterly / Event Driven / Before Expiry
Classification | Internal / Confidential
Status | Portfolio / Simulated

## Risk Acceptance Register
Acceptance ID | Vendor ID | Vendor Name | TPRM Tier | Risk Source | Risk ID | Risk Description | Inherent Likelihood | Inherent Impact | Inherent Score | Inherent Rating | Treatment Decision | Treatment Status | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Risk Tolerance Position | Acceptance Required | Business Justification | Business Impact | Security Impact | Compensating Controls | Risk Owner | Acceptance Authority | Request Date | Acceptance Start Date | Acceptance Expiry Date | Review Frequency | Next Review Date | Acceptance Status | Approval Decision | Approval Date | Approval Conditions | Monitoring Requirements | Risk Register Updated | Treatment Plan Updated | Exception Link | Evidence Reference | Closure Criteria | Closure Date | Escalation Required | Comments
ACC-RR-001 | VND-001 | CloudSphere Infrastructure | Enhanced | Residual Vendor Risk | VND-001-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 16 | High | Mitigate | In Progress | 3 | 3 | 9 | Medium | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-001 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-002 | VND-002 | Microsoft 365 Services | Standard | Residual Vendor Risk | VND-002-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 9 | Medium | Mitigate | In Progress | 2 | 2 | 4 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-002 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-003 | VND-003 | SecureVault Backup | Enhanced | Residual Vendor Risk | VND-003-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 16 | High | Mitigate | In Progress | 3 | 3 | 9 | Medium | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-003 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-004 | VND-004 | TalentCore HRMS | Standard | Residual Vendor Risk | VND-004-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 9 | Medium | Mitigate | In Progress | 2 | 2 | 4 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-004 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-005 | VND-005 | PayMatrix Solutions | Standard | Residual Vendor Risk | VND-005-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 9 | Medium | Mitigate | In Progress | 2 | 2 | 4 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-005 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-006 | VND-006 | SalesFlow CRM | Standard | Residual Vendor Risk | VND-006-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 9 | Medium | Mitigate | In Progress | 2 | 2 | 4 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-006 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-007 | VND-007 | NetShield SOC Services | Enhanced | Residual Vendor Risk | VND-007-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 16 | High | Mitigate | In Progress | 3 | 3 | 9 | Medium | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-007 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-008 | VND-008 | RedFort Security Testing | Standard | Residual Vendor Risk | VND-008-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 9 | Medium | Mitigate | In Progress | 2 | 2 | 4 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-008 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-009 | VND-009 | EndpointGuard Technologies | Enhanced | Residual Vendor Risk | VND-009-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 16 | High | Mitigate | In Progress | 3 | 3 | 9 | Medium | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-009 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-010 | VND-010 | ConnectNet Communications | Standard | Residual Vendor Risk | VND-010-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 9 | Medium | Mitigate | In Progress | 2 | 2 | 4 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-010 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-011 | VND-011 | DataCenterOne | Enhanced | Residual Vendor Risk | VND-011-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 16 | High | Mitigate | In Progress | 3 | 3 | 9 | Medium | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-011 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-012 | VND-012 | RecruitPro Services | Standard | Residual Vendor Risk | VND-012-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 9 | Medium | Mitigate | In Progress | 2 | 2 | 4 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-012 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-013 | VND-013 | FinLedger Systems | Standard | Residual Vendor Risk | VND-013-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 9 | Medium | Mitigate | In Progress | 2 | 2 | 4 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-013 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-014 | VND-014 | PayGate Services | Enhanced | Residual Vendor Risk | VND-014-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 16 | High | Mitigate | In Progress | 3 | 3 | 9 | Medium | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-014 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-015 | VND-015 | ServiceDesk Pro | Enhanced | Residual Vendor Risk | VND-015-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 16 | High | Mitigate | In Progress | 3 | 3 | 9 | Medium | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-015 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-016 | VND-016 | PrintSecure Solutions | Basic | Residual Vendor Risk | VND-016-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 4 | Low | Mitigate | In Progress | 1 | 1 | 1 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-016 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-017 | VND-017 | DocuSign Services | Standard | Residual Vendor Risk | VND-017-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 9 | Medium | Mitigate | In Progress | 2 | 2 | 4 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-017 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-018 | VND-018 | LegalEdge Associates | Basic | Residual Vendor Risk | VND-018-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 4 | Low | Mitigate | In Progress | 1 | 1 | 1 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-018 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-019 | VND-019 | ComplianceCheck Advisory | Basic | Residual Vendor Risk | VND-019-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 4 | Low | Mitigate | In Progress | 1 | 1 | 1 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-019 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-020 | VND-020 | SecureShred Services | Basic | Residual Vendor Risk | VND-020-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 4 | Low | Mitigate | In Progress | 1 | 1 | 1 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-020 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-021 | VND-021 | GuardForce Security | Basic | Residual Vendor Risk | VND-021-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 4 | Low | Mitigate | In Progress | 1 | 1 | 1 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-021 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-022 | VND-022 | SafeCam Systems | Basic | Residual Vendor Risk | VND-022-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 4 | Low | Mitigate | In Progress | 1 | 1 | 1 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-022 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-023 | VND-023 | OfficeNet Infrastructure | Standard | Residual Vendor Risk | VND-023-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 9 | Medium | Mitigate | In Progress | 2 | 2 | 4 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-023 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-024 | VND-024 | CodeSecure Labs | Standard | Residual Vendor Risk | VND-024-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 9 | Medium | Mitigate | In Progress | 2 | 2 | 4 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-024 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-025 | VND-025 | LearnSecure Training | Basic | Residual Vendor Risk | VND-025-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 4 | Low | Mitigate | In Progress | 1 | 1 | 1 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-025 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-026 | VND-026 | TeleSupport Services | Standard | Residual Vendor Risk | VND-026-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 9 | Medium | Mitigate | In Progress | 2 | 2 | 4 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-026 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-027 | VND-027 | MarketReach Analytics | Basic | Residual Vendor Risk | VND-027-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 4 | Low | Mitigate | In Progress | 1 | 1 | 1 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-027 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-028 | VND-028 | DevCloud Platform | Standard | Residual Vendor Risk | VND-028-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 9 | Medium | Mitigate | In Progress | 2 | 2 | 4 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-028 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-029 | VND-029 | DisasterReady DR Services | Enhanced | Residual Vendor Risk | VND-029-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 16 | High | Mitigate | In Progress | 3 | 3 | 9 | Medium | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-029 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.
ACC-RR-030 | VND-030 | SecureCourier Logistics | Basic | Residual Vendor Risk | VND-030-RISK | Residual third-party risk remaining after implemented/planned treatment. |  |  | 4 | Low | Mitigate | In Progress | 1 | 1 | 1 | Low | Within / Pending Tolerance Review | Yes | Temporary acceptance pending completion and validation of treatment actions. | To Be Assessed | To Be Assessed | Enhanced monitoring and compensating controls. | Risk Owner | Management | 2026-08-25 | 2026-08-25 | 2026-12-31 | Quarterly | 2026-09-30 | Pending | Pending |  | Acceptance subject to documented conditions and periodic review. | Monthly risk monitoring and treatment progress review. | Pending | Pending | EXC-030 | Simulated risk evidence. | Treatment completion or renewed formal acceptance. |  | No | Simulated acceptance record.

## Acceptance Approval Log
Approval ID | Acceptance ID | Vendor ID | Vendor Name | Approval Stage | Approver Role | Approver Name | Decision | Decision Date | Rationale / Conditions | Evidence Reference | Next Review Date | Comments
APR-RR-001 | ACC-RR-001 | VND-001 | CloudSphere Infrastructure | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-002 | ACC-RR-002 | VND-002 | Microsoft 365 Services | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-003 | ACC-RR-003 | VND-003 | SecureVault Backup | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-004 | ACC-RR-004 | VND-004 | TalentCore HRMS | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-005 | ACC-RR-005 | VND-005 | PayMatrix Solutions | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-006 | ACC-RR-006 | VND-006 | SalesFlow CRM | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-007 | ACC-RR-007 | VND-007 | NetShield SOC Services | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-008 | ACC-RR-008 | VND-008 | RedFort Security Testing | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-009 | ACC-RR-009 | VND-009 | EndpointGuard Technologies | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-010 | ACC-RR-010 | VND-010 | ConnectNet Communications | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-011 | ACC-RR-011 | VND-011 | DataCenterOne | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-012 | ACC-RR-012 | VND-012 | RecruitPro Services | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-013 | ACC-RR-013 | VND-013 | FinLedger Systems | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-014 | ACC-RR-014 | VND-014 | PayGate Services | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-015 | ACC-RR-015 | VND-015 | ServiceDesk Pro | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-016 | ACC-RR-016 | VND-016 | PrintSecure Solutions | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-017 | ACC-RR-017 | VND-017 | DocuSign Services | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-018 | ACC-RR-018 | VND-018 | LegalEdge Associates | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-019 | ACC-RR-019 | VND-019 | ComplianceCheck Advisory | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-020 | ACC-RR-020 | VND-020 | SecureShred Services | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-021 | ACC-RR-021 | VND-021 | GuardForce Security | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-022 | ACC-RR-022 | VND-022 | SafeCam Systems | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-023 | ACC-RR-023 | VND-023 | OfficeNet Infrastructure | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-024 | ACC-RR-024 | VND-024 | CodeSecure Labs | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-025 | ACC-RR-025 | VND-025 | LearnSecure Training | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-026 | ACC-RR-026 | VND-026 | TeleSupport Services | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-027 | ACC-RR-027 | VND-027 | MarketReach Analytics | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-028 | ACC-RR-028 | VND-028 | DevCloud Platform | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-029 | ACC-RR-029 | VND-029 | DisasterReady DR Services | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.
APR-RR-030 | ACC-RR-030 | VND-030 | SecureCourier Logistics | Initial Risk Acceptance | Management | Simulated Approver | Pending |  | Formal approval after residual-risk review. | Pending | 2026-09-30 | Simulated approval record.

## Acceptance Review Log
Review ID | Acceptance ID | Vendor ID | Vendor Name | Previous Residual Rating | Current Residual Rating | Risk Movement | Material Change | Incident Since Acceptance | Treatment Progress | Control Effectiveness | Acceptance Still Valid | New Expiry Date | Reviewer | Review Date | Decision | Actions | Evidence Reference | Comments
REV-ACC-001 | ACC-RR-001 | VND-001 | CloudSphere Infrastructure | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-002 | ACC-RR-002 | VND-002 | Microsoft 365 Services | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-003 | ACC-RR-003 | VND-003 | SecureVault Backup | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-004 | ACC-RR-004 | VND-004 | TalentCore HRMS | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-005 | ACC-RR-005 | VND-005 | PayMatrix Solutions | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-006 | ACC-RR-006 | VND-006 | SalesFlow CRM | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-007 | ACC-RR-007 | VND-007 | NetShield SOC Services | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-008 | ACC-RR-008 | VND-008 | RedFort Security Testing | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-009 | ACC-RR-009 | VND-009 | EndpointGuard Technologies | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-010 | ACC-RR-010 | VND-010 | ConnectNet Communications | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-011 | ACC-RR-011 | VND-011 | DataCenterOne | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-012 | ACC-RR-012 | VND-012 | RecruitPro Services | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-013 | ACC-RR-013 | VND-013 | FinLedger Systems | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-014 | ACC-RR-014 | VND-014 | PayGate Services | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-015 | ACC-RR-015 | VND-015 | ServiceDesk Pro | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-016 | ACC-RR-016 | VND-016 | PrintSecure Solutions | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-017 | ACC-RR-017 | VND-017 | DocuSign Services | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-018 | ACC-RR-018 | VND-018 | LegalEdge Associates | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-019 | ACC-RR-019 | VND-019 | ComplianceCheck Advisory | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-020 | ACC-RR-020 | VND-020 | SecureShred Services | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-021 | ACC-RR-021 | VND-021 | GuardForce Security | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-022 | ACC-RR-022 | VND-022 | SafeCam Systems | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-023 | ACC-RR-023 | VND-023 | OfficeNet Infrastructure | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-024 | ACC-RR-024 | VND-024 | CodeSecure Labs | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-025 | ACC-RR-025 | VND-025 | LearnSecure Training | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-026 | ACC-RR-026 | VND-026 | TeleSupport Services | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-027 | ACC-RR-027 | VND-027 | MarketReach Analytics | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-028 | ACC-RR-028 | VND-028 | DevCloud Platform | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-029 | ACC-RR-029 | VND-029 | DisasterReady DR Services | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.
REV-ACC-030 | ACC-RR-030 | VND-030 | SecureCourier Logistics | Pending | Pending | No Change | No | No | In Progress | Pending | Pending | 2026-12-31 | GRC Analyst |  | Pending | Complete reassessment and update acceptance if required. | Pending | Simulated review.

## Acceptance Expiry Monitoring
Monitor ID | Acceptance ID | Vendor ID | Vendor Name | Expiry Date | Days to Expiry | Residual Rating | Approval Status | Review Status | Owner | Escalation Required | Action Required | Renewal Decision | Comments
MON-ACC-001 | ACC-RR-001 | VND-001 | CloudSphere Infrastructure | 2026-12-31 | 128 | High | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-002 | ACC-RR-002 | VND-002 | Microsoft 365 Services | 2026-12-31 | 128 | Medium | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-003 | ACC-RR-003 | VND-003 | SecureVault Backup | 2026-12-31 | 128 | High | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-004 | ACC-RR-004 | VND-004 | TalentCore HRMS | 2026-12-31 | 128 | Medium | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-005 | ACC-RR-005 | VND-005 | PayMatrix Solutions | 2026-12-31 | 128 | Medium | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-006 | ACC-RR-006 | VND-006 | SalesFlow CRM | 2026-12-31 | 128 | Medium | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-007 | ACC-RR-007 | VND-007 | NetShield SOC Services | 2026-12-31 | 128 | High | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-008 | ACC-RR-008 | VND-008 | RedFort Security Testing | 2026-12-31 | 128 | Medium | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-009 | ACC-RR-009 | VND-009 | EndpointGuard Technologies | 2026-12-31 | 128 | High | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-010 | ACC-RR-010 | VND-010 | ConnectNet Communications | 2026-12-31 | 128 | Medium | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-011 | ACC-RR-011 | VND-011 | DataCenterOne | 2026-12-31 | 128 | High | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-012 | ACC-RR-012 | VND-012 | RecruitPro Services | 2026-12-31 | 128 | Medium | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-013 | ACC-RR-013 | VND-013 | FinLedger Systems | 2026-12-31 | 128 | Medium | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-014 | ACC-RR-014 | VND-014 | PayGate Services | 2026-12-31 | 128 | High | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-015 | ACC-RR-015 | VND-015 | ServiceDesk Pro | 2026-12-31 | 128 | High | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-016 | ACC-RR-016 | VND-016 | PrintSecure Solutions | 2026-12-31 | 128 | Low | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-017 | ACC-RR-017 | VND-017 | DocuSign Services | 2026-12-31 | 128 | Medium | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-018 | ACC-RR-018 | VND-018 | LegalEdge Associates | 2026-12-31 | 128 | Low | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-019 | ACC-RR-019 | VND-019 | ComplianceCheck Advisory | 2026-12-31 | 128 | Low | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-020 | ACC-RR-020 | VND-020 | SecureShred Services | 2026-12-31 | 128 | Low | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-021 | ACC-RR-021 | VND-021 | GuardForce Security | 2026-12-31 | 128 | Low | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-022 | ACC-RR-022 | VND-022 | SafeCam Systems | 2026-12-31 | 128 | Low | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-023 | ACC-RR-023 | VND-023 | OfficeNet Infrastructure | 2026-12-31 | 128 | Medium | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-024 | ACC-RR-024 | VND-024 | CodeSecure Labs | 2026-12-31 | 128 | Medium | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-025 | ACC-RR-025 | VND-025 | LearnSecure Training | 2026-12-31 | 128 | Low | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-026 | ACC-RR-026 | VND-026 | TeleSupport Services | 2026-12-31 | 128 | Medium | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-027 | ACC-RR-027 | VND-027 | MarketReach Analytics | 2026-12-31 | 128 | Low | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-028 | ACC-RR-028 | VND-028 | DevCloud Platform | 2026-12-31 | 128 | Medium | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-029 | ACC-RR-029 | VND-029 | DisasterReady DR Services | 2026-12-31 | 128 | High | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
MON-ACC-030 | ACC-RR-030 | VND-030 | SecureCourier Logistics | 2026-12-31 | 128 | Low | Pending | Pending | GRC Manager | No | Complete risk review before expiry | Pending | Simulated expiry monitoring.
Formulas:
Days to Expiry = [Expiry Date]-TODAY()

## Executive Summary
Metric | Value | Management Interpretation | Residual Rating | Count
Vendor Population | 30 | Current residual risk acceptance population | Critical | 0
Acceptance Records | 30 | Formal acceptance lifecycle records | High | 0
Approval Records | 30 | Approval workflow population | Medium | 8
Review Records | 30 | Periodic acceptance review population | Low | 22
Expiry Records | 30 | Time-bound acceptance monitoring
Approved / Conditional | 0 | Accepted residual risk population
Expired | 0 | Requires immediate review
High/Critical Residual Risk | 0 | Priority risk acceptance population
Open / Pending | 30 | Awaiting formal decision
Renewal / Review Required | 30 | Acceptance validity requiring review

## Acceptance Methodology
Area | Guidance | Rule
Residual Risk | Risk remaining after controls/treatment | Use current evidence and reassessment
Acceptance Decision | Formal decision to retain residual risk | Must be within or explicitly approved above tolerance
Authority | Assign approval based on risk level | Requester should not be sole approver
Conditions | Document conditions attached to acceptance | Track conditions as actions
Expiry | Set defined validity period | Review before expiry
Monitoring | Track incidents, control effectiveness and treatment progress | Revoke/reassess if risk materially changes
Closure | Close when treatment removes need for acceptance or risk decision changes | Update risk register and evidence

## Data Dictionary
Field | Purpose
Acceptance ID | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Vendor ID | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Vendor Name | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
TPRM Tier | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Risk Source | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Risk ID | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Risk Description | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Inherent Likelihood | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Inherent Impact | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Inherent Score | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Inherent Rating | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Treatment Decision | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Treatment Status | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Residual Likelihood | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Residual Impact | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Residual Score | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Residual Rating | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Risk Tolerance Position | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Acceptance Required | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Business Justification | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Business Impact | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Security Impact | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Compensating Controls | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Risk Owner | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Acceptance Authority | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Request Date | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Acceptance Start Date | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Acceptance Expiry Date | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Review Frequency | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Next Review Date | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Acceptance Status | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Approval Decision | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Approval Date | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Approval Conditions | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Monitoring Requirements | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Risk Register Updated | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Treatment Plan Updated | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Exception Link | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Evidence Reference | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Closure Criteria | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Closure Date | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Escalation Required | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.
Comments | Field used to document residual risk, business rationale, acceptance authority, conditions, monitoring, expiry and closure.