## README
TPRM-025 ¦ VENDOR RISK ESCALATION & MANAGEMENT ACTION REGISTER | Mayekar Technologies Pvt. Ltd.
Document ID | MTPL-TPRM-025
Version | 1.0
Prepared By | Omkar Abhay Mayekar
Status | Portfolio / Simulated Evidence
Purpose | Central register for escalating material vendor risks and tracking management actions through ownership, deadlines, escalation levels, evidence, validation and closure.
Escalation Triggers | Critical/high residual risk, overdue remediation, control failure, material incident, repeated SLA/security failure, expired risk acceptance, regulatory impact or significant vendor change.
Management Principle | Escalation should be proportionate to risk and should result in an accountable decision, action, deadline and evidence of closure/validation.
Lifecycle | Identify → Assess → Escalate → Assign → Remediate → Validate → Close / Re-escalate.
Disclaimer | All records, actions, priorities, dates and management decisions are simulated for portfolio/learning purposes.

## Document Control
Field | Value
Document Title | Vendor Risk Escalation & Management Action Register
Document ID | MTPL-TPRM-025
Version | 1.0
Organization | Mayekar Technologies Pvt. Ltd.
Prepared By | Omkar Abhay Mayekar
Reviewed By | GRC Manager — Simulated
Approved By | Management — Simulated
Effective Date | 2026-08-01
Review Cycle | Monthly / Event Driven
Classification | Internal / Confidential
Status | Portfolio / Simulated

## Escalation Action Register
Action ID | Vendor ID | Vendor Name | TPRM Tier | Current Risk Rating | Trigger Category | Trigger Description | Source / Risk ID | Business Impact | Security Impact | Escalation Level | Escalation Reason | Date Identified | Escalation Date | Management Decision | Action Required | Action Owner | Supporting Owner | Priority | Target Date | Status | Progress % | Dependency | Risk Treatment Link | Risk Acceptance Link | Exception Link | Evidence Required | Evidence Reference | Validation Required | Validation Status | Overdue Days | Escalation Required | Escalated To | Escalation Date 2 | Resolution / Outcome | Closure Evidence | Closure Date | Risk Register Updated | Management Comment
ESC-001 | VND-001 | CloudSphere Infrastructure | Enhanced | Residual Vendor Risk | Critical / High Residual Risk | Material vendor risk requiring management attention. | VND-001-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-001-RTP | ACC-RR-001 | EXC-001 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-002 | VND-002 | Microsoft 365 Services | Standard | Residual Vendor Risk | Overdue Remediation | Material vendor risk requiring management attention. | VND-002-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-002-RTP | ACC-RR-002 | EXC-002 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-003 | VND-003 | SecureVault Backup | Enhanced | Residual Vendor Risk | Security Incident | Material vendor risk requiring management attention. | VND-003-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-003-RTP | ACC-RR-003 | EXC-003 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-004 | VND-004 | TalentCore HRMS | Standard | Residual Vendor Risk | Control Failure | Material vendor risk requiring management attention. | VND-004-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-004-RTP | ACC-RR-004 | EXC-004 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-005 | VND-005 | PayMatrix Solutions | Standard | Residual Vendor Risk | SLA / Performance Failure | Material vendor risk requiring management attention. | VND-005-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-005-RTP | ACC-RR-005 | EXC-005 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-006 | VND-006 | SalesFlow CRM | Standard | Residual Vendor Risk | Expired Risk Acceptance | Material vendor risk requiring management attention. | VND-006-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-006-RTP | ACC-RR-006 | EXC-006 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-007 | VND-007 | NetShield SOC Services | Enhanced | Residual Vendor Risk | Regulatory / Compliance Change | Material vendor risk requiring management attention. | VND-007-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-007-RTP | ACC-RR-007 | EXC-007 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-008 | VND-008 | RedFort Security Testing | Standard | Residual Vendor Risk | Material Vendor Change | Material vendor risk requiring management attention. | VND-008-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-008-RTP | ACC-RR-008 | EXC-008 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-009 | VND-009 | EndpointGuard Technologies | Enhanced | Residual Vendor Risk | Audit Finding | Material vendor risk requiring management attention. | VND-009-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-009-RTP | ACC-RR-009 | EXC-009 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-010 | VND-010 | ConnectNet Communications | Standard | Residual Vendor Risk | Other | Material vendor risk requiring management attention. | VND-010-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-010-RTP | ACC-RR-010 | EXC-010 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-011 | VND-011 | DataCenterOne | Enhanced | Residual Vendor Risk | Critical / High Residual Risk | Material vendor risk requiring management attention. | VND-011-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-011-RTP | ACC-RR-011 | EXC-011 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-012 | VND-012 | RecruitPro Services | Standard | Residual Vendor Risk | Overdue Remediation | Material vendor risk requiring management attention. | VND-012-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-012-RTP | ACC-RR-012 | EXC-012 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-013 | VND-013 | FinLedger Systems | Standard | Residual Vendor Risk | Security Incident | Material vendor risk requiring management attention. | VND-013-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-013-RTP | ACC-RR-013 | EXC-013 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-014 | VND-014 | PayGate Services | Enhanced | Residual Vendor Risk | Control Failure | Material vendor risk requiring management attention. | VND-014-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-014-RTP | ACC-RR-014 | EXC-014 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-015 | VND-015 | ServiceDesk Pro | Enhanced | Residual Vendor Risk | SLA / Performance Failure | Material vendor risk requiring management attention. | VND-015-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-015-RTP | ACC-RR-015 | EXC-015 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-016 | VND-016 | PrintSecure Solutions | Basic | Residual Vendor Risk | Expired Risk Acceptance | Material vendor risk requiring management attention. | VND-016-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-016-RTP | ACC-RR-016 | EXC-016 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-017 | VND-017 | DocuSign Services | Standard | Residual Vendor Risk | Regulatory / Compliance Change | Material vendor risk requiring management attention. | VND-017-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-017-RTP | ACC-RR-017 | EXC-017 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-018 | VND-018 | LegalEdge Associates | Basic | Residual Vendor Risk | Material Vendor Change | Material vendor risk requiring management attention. | VND-018-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-018-RTP | ACC-RR-018 | EXC-018 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-019 | VND-019 | ComplianceCheck Advisory | Basic | Residual Vendor Risk | Audit Finding | Material vendor risk requiring management attention. | VND-019-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-019-RTP | ACC-RR-019 | EXC-019 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-020 | VND-020 | SecureShred Services | Basic | Residual Vendor Risk | Other | Material vendor risk requiring management attention. | VND-020-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-020-RTP | ACC-RR-020 | EXC-020 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-021 | VND-021 | GuardForce Security | Basic | Residual Vendor Risk | Critical / High Residual Risk | Material vendor risk requiring management attention. | VND-021-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-021-RTP | ACC-RR-021 | EXC-021 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-022 | VND-022 | SafeCam Systems | Basic | Residual Vendor Risk | Overdue Remediation | Material vendor risk requiring management attention. | VND-022-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-022-RTP | ACC-RR-022 | EXC-022 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-023 | VND-023 | OfficeNet Infrastructure | Standard | Residual Vendor Risk | Security Incident | Material vendor risk requiring management attention. | VND-023-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-023-RTP | ACC-RR-023 | EXC-023 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-024 | VND-024 | CodeSecure Labs | Standard | Residual Vendor Risk | Control Failure | Material vendor risk requiring management attention. | VND-024-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-024-RTP | ACC-RR-024 | EXC-024 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-025 | VND-025 | LearnSecure Training | Basic | Residual Vendor Risk | SLA / Performance Failure | Material vendor risk requiring management attention. | VND-025-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-025-RTP | ACC-RR-025 | EXC-025 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-026 | VND-026 | TeleSupport Services | Standard | Residual Vendor Risk | Expired Risk Acceptance | Material vendor risk requiring management attention. | VND-026-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-026-RTP | ACC-RR-026 | EXC-026 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-027 | VND-027 | MarketReach Analytics | Basic | Residual Vendor Risk | Regulatory / Compliance Change | Material vendor risk requiring management attention. | VND-027-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-027-RTP | ACC-RR-027 | EXC-027 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-028 | VND-028 | DevCloud Platform | Standard | Residual Vendor Risk | Material Vendor Change | Material vendor risk requiring management attention. | VND-028-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-028-RTP | ACC-RR-028 | EXC-028 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-029 | VND-029 | DisasterReady DR Services | Enhanced | Residual Vendor Risk | Audit Finding | Material vendor risk requiring management attention. | VND-029-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-029-RTP | ACC-RR-029 | EXC-029 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.
ESC-030 | VND-030 | SecureCourier Logistics | Basic | Residual Vendor Risk | Other | Material vendor risk requiring management attention. | VND-030-RISK | To Be Assessed | To Be Assessed | Level 2 — GRC Manager | Risk requires accountable action and monitoring. | 2026-08-25 | 2026-08-25 | Pending | Review root cause, define corrective action, assign owner and validate closure. | Vendor Manager | GRC Analyst | Medium | 2026-10-31 | Open | 0 | Business/security owner availability | VND-030-RTP | ACC-RR-030 | EXC-030 | Objective remediation evidence |  | Yes | Pending | 0 | No | GRC Manager |  | Pending | Pending |  | Pending | Simulated management action.

## Escalation Log
Escalation ID | Action ID | Vendor ID | Vendor Name | Escalation Level | Escalated From | Escalated To | Escalation Date | Reason | Decision Required | Response Due Date | Response Received Date | Decision | Conditions | Evidence Reference | Status | Comments
ESCLOG-001 | ESC-001 | VND-001 | CloudSphere Infrastructure | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-002 | ESC-002 | VND-002 | Microsoft 365 Services | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-003 | ESC-003 | VND-003 | SecureVault Backup | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-004 | ESC-004 | VND-004 | TalentCore HRMS | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-005 | ESC-005 | VND-005 | PayMatrix Solutions | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-006 | ESC-006 | VND-006 | SalesFlow CRM | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-007 | ESC-007 | VND-007 | NetShield SOC Services | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-008 | ESC-008 | VND-008 | RedFort Security Testing | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-009 | ESC-009 | VND-009 | EndpointGuard Technologies | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-010 | ESC-010 | VND-010 | ConnectNet Communications | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-011 | ESC-011 | VND-011 | DataCenterOne | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-012 | ESC-012 | VND-012 | RecruitPro Services | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-013 | ESC-013 | VND-013 | FinLedger Systems | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-014 | ESC-014 | VND-014 | PayGate Services | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-015 | ESC-015 | VND-015 | ServiceDesk Pro | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-016 | ESC-016 | VND-016 | PrintSecure Solutions | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-017 | ESC-017 | VND-017 | DocuSign Services | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-018 | ESC-018 | VND-018 | LegalEdge Associates | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-019 | ESC-019 | VND-019 | ComplianceCheck Advisory | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-020 | ESC-020 | VND-020 | SecureShred Services | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-021 | ESC-021 | VND-021 | GuardForce Security | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-022 | ESC-022 | VND-022 | SafeCam Systems | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-023 | ESC-023 | VND-023 | OfficeNet Infrastructure | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-024 | ESC-024 | VND-024 | CodeSecure Labs | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-025 | ESC-025 | VND-025 | LearnSecure Training | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-026 | ESC-026 | VND-026 | TeleSupport Services | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-027 | ESC-027 | VND-027 | MarketReach Analytics | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-028 | ESC-028 | VND-028 | DevCloud Platform | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-029 | ESC-029 | VND-029 | DisasterReady DR Services | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.
ESCLOG-030 | ESC-030 | VND-030 | SecureCourier Logistics | Level 2 — GRC Manager | Vendor Manager | GRC Manager | 2026-08-25 | Material vendor risk requires management decision. | Approve action plan and remediation deadline. | 2026-09-05 |  | Pending | Document conditions if approved. | Pending | Open | Simulated escalation log.

## Management Action Tracker
Management Action ID | Action ID | Vendor ID | Vendor Name | Action Category | Action Description | Owner | Priority | Start Date | Target Date | Status | Progress % | Blocker | Dependency | Evidence Required | Evidence Reference | Validation | Validation Date | Closure Date | Outcome | Comments
MA-001 | ESC-001 | VND-001 | CloudSphere Infrastructure | Risk Treatment | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-002 | ESC-002 | VND-002 | Microsoft 365 Services | Control Remediation | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-003 | ESC-003 | VND-003 | SecureVault Backup | Contractual Remediation | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-004 | ESC-004 | VND-004 | TalentCore HRMS | Security Improvement | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-005 | ESC-005 | VND-005 | PayMatrix Solutions | Incident Corrective Action | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-006 | ESC-006 | VND-006 | SalesFlow CRM | SLA Improvement | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-007 | ESC-007 | VND-007 | NetShield SOC Services | Compliance Action | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-008 | ESC-008 | VND-008 | RedFort Security Testing | Risk Treatment | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-009 | ESC-009 | VND-009 | EndpointGuard Technologies | Control Remediation | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-010 | ESC-010 | VND-010 | ConnectNet Communications | Contractual Remediation | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-011 | ESC-011 | VND-011 | DataCenterOne | Security Improvement | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-012 | ESC-012 | VND-012 | RecruitPro Services | Incident Corrective Action | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-013 | ESC-013 | VND-013 | FinLedger Systems | SLA Improvement | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-014 | ESC-014 | VND-014 | PayGate Services | Compliance Action | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-015 | ESC-015 | VND-015 | ServiceDesk Pro | Risk Treatment | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-016 | ESC-016 | VND-016 | PrintSecure Solutions | Control Remediation | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-017 | ESC-017 | VND-017 | DocuSign Services | Contractual Remediation | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-018 | ESC-018 | VND-018 | LegalEdge Associates | Security Improvement | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-019 | ESC-019 | VND-019 | ComplianceCheck Advisory | Incident Corrective Action | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-020 | ESC-020 | VND-020 | SecureShred Services | SLA Improvement | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-021 | ESC-021 | VND-021 | GuardForce Security | Compliance Action | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-022 | ESC-022 | VND-022 | SafeCam Systems | Risk Treatment | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-023 | ESC-023 | VND-023 | OfficeNet Infrastructure | Control Remediation | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-024 | ESC-024 | VND-024 | CodeSecure Labs | Contractual Remediation | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-025 | ESC-025 | VND-025 | LearnSecure Training | Security Improvement | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-026 | ESC-026 | VND-026 | TeleSupport Services | Incident Corrective Action | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-027 | ESC-027 | VND-027 | MarketReach Analytics | SLA Improvement | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-028 | ESC-028 | VND-028 | DevCloud Platform | Compliance Action | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-029 | ESC-029 | VND-029 | DisasterReady DR Services | Risk Treatment | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.
MA-030 | ESC-030 | VND-030 | SecureCourier Logistics | Control Remediation | Implement agreed corrective action and provide objective evidence. | Vendor Manager | Medium | 2026-08-25 | 2026-10-31 | Open | 0 | None | Business/security dependency | Objective closure evidence |  | Pending |  |  | Pending | Simulated action.

## Action Review Log
Review ID | Management Action ID | Vendor ID | Vendor Name | Review Date | Previous Status | Current Status | Progress % | Target Date | Days Overdue | Risk Changed | Incident / Change | Blocker | Decision | Escalate Further | Reviewer | Evidence Reference | Comments
REV-MA-001 | MA-001 | VND-001 | CloudSphere Infrastructure | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-002 | MA-002 | VND-002 | Microsoft 365 Services | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-003 | MA-003 | VND-003 | SecureVault Backup | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-004 | MA-004 | VND-004 | TalentCore HRMS | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-005 | MA-005 | VND-005 | PayMatrix Solutions | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-006 | MA-006 | VND-006 | SalesFlow CRM | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-007 | MA-007 | VND-007 | NetShield SOC Services | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-008 | MA-008 | VND-008 | RedFort Security Testing | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-009 | MA-009 | VND-009 | EndpointGuard Technologies | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-010 | MA-010 | VND-010 | ConnectNet Communications | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-011 | MA-011 | VND-011 | DataCenterOne | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-012 | MA-012 | VND-012 | RecruitPro Services | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-013 | MA-013 | VND-013 | FinLedger Systems | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-014 | MA-014 | VND-014 | PayGate Services | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-015 | MA-015 | VND-015 | ServiceDesk Pro | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-016 | MA-016 | VND-016 | PrintSecure Solutions | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-017 | MA-017 | VND-017 | DocuSign Services | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-018 | MA-018 | VND-018 | LegalEdge Associates | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-019 | MA-019 | VND-019 | ComplianceCheck Advisory | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-020 | MA-020 | VND-020 | SecureShred Services | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-021 | MA-021 | VND-021 | GuardForce Security | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-022 | MA-022 | VND-022 | SafeCam Systems | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-023 | MA-023 | VND-023 | OfficeNet Infrastructure | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-024 | MA-024 | VND-024 | CodeSecure Labs | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-025 | MA-025 | VND-025 | LearnSecure Training | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-026 | MA-026 | VND-026 | TeleSupport Services | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-027 | MA-027 | VND-027 | MarketReach Analytics | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-028 | MA-028 | VND-028 | DevCloud Platform | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-029 | MA-029 | VND-029 | DisasterReady DR Services | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.
REV-MA-030 | MA-030 | VND-030 | SecureCourier Logistics | 2026-09-30 | Open | Open | 0 | 2026-10-31 | 0 | No | No | None | Continue remediation | No | GRC Analyst | Pending | Simulated review.

## Executive Summary
Metric | Value | Management Interpretation | Priority | Count
Vendor Population | 30 | Current escalation and management-action population | Critical | 0
Escalation Records | 30 | Baseline escalation records | High | 0
Management Actions | 30 | Corrective action workload | Medium | 30
Escalation Log Records | 30 | Formal escalation workflow | Low | 0
Review Records | 30 | Periodic action review population
Critical / High Actions | 0 | Priority management workload
Blocked Actions | 0 | Requires management intervention
Open Actions | 30 | Active remediation workload
Pending Validation | 0 | Closure assurance backlog
Further Escalation Required | 0 | Needs higher management attention

## Escalation Methodology
Area | Guidance | Rule
Trigger | Identify material risk, failure or overdue obligation | Document objective trigger and source
Escalation Level | Escalate proportionately to risk and decision authority | Critical issues should reach appropriate senior management
Management Action | Define one accountable action, owner and target date | Avoid actions without measurable closure criteria
Monitoring | Review progress and changing risk | Blocked/overdue items require intervention
Validation | Confirm remediation/control effectiveness | Closure requires objective evidence
Re-escalation | Escalate when risk increases or action is blocked | Do not allow repeated deadline slippage without decision
Closure | Document outcome and update risk/treatment records | Retain closure evidence

## Data Dictionary
Field | Purpose
Action ID | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Vendor ID | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Vendor Name | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
TPRM Tier | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Current Risk Rating | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Trigger Category | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Trigger Description | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Source / Risk ID | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Business Impact | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Security Impact | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Escalation Level | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Escalation Reason | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Date Identified | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Escalation Date | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Management Decision | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Action Required | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Action Owner | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Supporting Owner | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Priority | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Target Date | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Status | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Progress % | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Dependency | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Risk Treatment Link | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Risk Acceptance Link | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Exception Link | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Evidence Required | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Evidence Reference | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Validation Required | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Validation Status | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Overdue Days | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Escalation Required | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Escalated To | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Escalation Date 2 | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Resolution / Outcome | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Closure Evidence | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Closure Date | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Risk Register Updated | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.
Management Comment | Field used to document vendor risk escalation, management decisions, corrective actions, deadlines, evidence, validation and closure.