## Audit Readiness Checklist
Check ID | Audit Area | Requirement / Checkpoint | Related TPRM Document(s) | Expected Evidence | Owner | Frequency | Readiness Status | Evidence Status | Finding / Gap | Corrective Action | Priority | Target Date | Auditor Notes
AR-001 | Governance | TPRM program scope and objectives are formally defined. | TPRM-001 | Approved program charter | TPRM Manager | Annual | Ready | Available |  |  | High
AR-002 | Governance | TPRM roles, responsibilities and decision authority are defined. | TPRM-002 | Approved RACI / responsibility matrix | TPRM Manager | Annual | Ready | Available |  |  | High
AR-003 | Policy | TPRM policy is documented, reviewed and approved. | TPRM-003 | Approved policy and review record | TPRM Manager | Annual | Pending Verification | Pending |  |  | High
AR-004 | Procedure | Vendor management and lifecycle procedures are documented. | TPRM-004 / TPRM-005 | Approved procedures and workflow | Vendor Manager | Annual | Pending Verification | Pending |  |  | High
AR-005 | Inventory | Complete vendor inventory is maintained. | TPRM-006 | Current vendor inventory | Vendor Manager | Monthly | Pending Verification | Pending |  |  | High
AR-006 | Risk Assessment | Vendor risk assessments are completed using defined criteria. | TPRM-007 / TPRM-008 | Completed risk assessments | GRC Analyst | At onboarding / periodic | Pending Verification | Pending |  |  | High
AR-007 | Risk Register | Vendor risks are centrally recorded with owners and ratings. | TPRM-009 | Current vendor risk register | Risk Owner | Monthly | Pending Verification | Pending |  |  | High
AR-008 | Due Diligence | Due diligence is performed according to vendor risk/tier. | TPRM-010 / TPRM-021 | Due diligence records | GRC Analyst | Onboarding / periodic | Pending Verification | Pending |  |  | High
AR-009 | Security Assessment | Security questionnaires and assurance evidence are reviewed. | TPRM-011 / TPRM-012 / TPRM-022 | Questionnaire and evidence review | Security / GRC | Risk-based | Pending Verification | Pending |  |  | High
AR-010 | Contracts | Security, privacy and SLA requirements are reflected in contracts. | TPRM-013 | Contract/SLA/security review record | Legal / Vendor Manager | Contract event | Pending Verification | Pending |  |  | High
AR-011 | SLA | Vendor performance and SLA commitments are monitored. | TPRM-014 / TPRM-028 | SLA reports and breach records | Vendor Manager | Monthly | Pending Verification | Pending |  |  | Medium
AR-012 | Incident | Vendor incidents and security events are recorded and managed. | TPRM-015 / TPRM-027 | Incident/event records | Security Incident Owner | Event-driven | Pending Verification | Pending |  |  | High
AR-013 | BCDR | Critical vendors undergo BCDR assessment and testing. | TPRM-016 / TPRM-029 | BCDR assessment/test evidence | BCM Owner | Annual / risk-based | Pending Verification | Pending |  |  | High
AR-014 | Risk Treatment | Risk treatment actions have owners, dates and closure evidence. | TPRM-017 | Treatment/remediation register | Risk Owner | Monthly | Pending Verification | Pending |  |  | High
AR-015 | Reassessment | Vendor risks are periodically reassessed and material-change triggers exist. | TPRM-018 / TPRM-026 | Reassessment and monitoring records | GRC Analyst | Periodic / event-driven | Pending Verification | Pending |  |  | High
AR-016 | Offboarding | Vendor exit, access revocation and data closure are documented. | TPRM-019 | Completed offboarding checklist | Vendor Manager / IT | Exit event | Pending Verification | Pending |  |  | High
AR-017 | Management Reporting | Management receives TPRM risk and performance reporting. | TPRM-020 | Dashboard / management report | TPRM Manager | Monthly / quarterly | Ready | Available |  |  | Medium
AR-018 | Periodic Review | Due diligence and security posture are periodically reviewed. | TPRM-021 / TPRM-022 | Periodic review records | GRC Analyst | Periodic | Pending Verification | Pending |  |  | Medium
AR-019 | Exceptions | Security exceptions/waivers are formally approved and time-bound. | TPRM-023 | Exception/waiver approval | Risk Owner | Event-driven | Pending Verification | Pending |  |  | High
AR-020 | Risk Acceptance | Residual risk acceptance has rationale, owner, approver and expiry. | TPRM-024 | Risk acceptance records | Risk Owner / Management | Event-driven | Pending Verification | Pending |  |  | High
AR-021 | Escalation | High/critical or unacceptable vendor risks are escalated. | TPRM-025 | Escalation record / decision | TPRM Manager | Event-driven | Pending Verification | Pending |  |  | High
AR-022 | Monitoring | Continuous monitoring indicators and triggers are defined. | TPRM-026 | Monitoring records / alerts | GRC Analyst | Continuous | Pending Verification | Pending |  |  | High
AR-023 | Privacy | Vendor privacy and data protection requirements are assessed. | TPRM-030 | Privacy assessment / DPA review | Privacy / GRC | Risk-based / periodic | Pending Verification | Pending |  |  | High
AR-024 | Evidence | Evidence is indexed, traceable and validated. | Evidence Index / Validation Mapping | Evidence register and validation records | GRC Analyst | Continuous | Pending Verification | Pending |  |  | High
AR-025 | Corrective Action | Findings have documented corrective actions and validation. | TPRM-017 / Validation Mapping | Finding, action and closure evidence | Risk Owner | Monthly | Pending Verification | Pending |  |  | High
AR-026 | KPI/KRI | TPRM KPIs/KRIs have definitions, thresholds and owners. | KPI/KRI Summary | KPI/KRI register and dashboard | TPRM Manager | Monthly | Ready | Available |  |  | Medium
AR-027 | Cross-Document Traceability | Key records can be traced across the TPRM lifecycle. | Cross-Document Validation Report | Cross-document validation matrix | GRC Analyst | Quarterly | Pending Verification | Pending |  |  | High
AR-028 | Document Control | Document IDs, versions, approvals and review dates are consistent. | TPRM-001 to TPRM-030 | Document control metadata | Document Owner | Annual / change | Pending Verification | Pending |  |  | High
AR-029 | GitHub Safety | Portfolio contains no real confidential/vendor-sensitive information. | README / Evidence Pack | Repository content review | Portfolio Owner | Before release | Ready | Available |  |  | Critical
AR-030 | Audit Readiness | Management can demonstrate governance, risk, evidence and remediation traceability. | All TPRM deliverables | Audit evidence pack and management report | TPRM Manager | Audit event | Pending Verification | Pending |  |  | Critical

## Readiness Summary
TPRM AUDIT READINESS SUMMARY | Mayekar Technologies Pvt. Ltd.
Scope | 30 audit-readiness checkpoints covering TPRM governance, risk, evidence, monitoring and management reporting.
Ready Checkpoints | 5 | Currently supported by portfolio deliverables.
Pending Verification | 25 | Requires direct file/evidence validation.
Partially Ready | 0 | Some supporting evidence or controls remain.
Evidence Available | 5 | Evidence is marked available in the portfolio.
Evidence Pending | 25 | Evidence requires collection or validation.
Overall Readiness | Conditional | Portfolio is not audit-ready until all pending verification items are directly validated.
Release Recommendation | Complete final file-level QA, cross-document validation and evidence validation before representing the portfolio as fully audit-ready.

## Audit Evidence Request
Request ID | Audit Evidence Requested | Related TPRM Area | Primary Source | Minimum Evidence Expected | Status
AER-001 | Approved TPRM charter and governance approval | Governance | TPRM-001 | Current approved version with approval record | Pending
AER-002 | TPRM roles and decision authority | Governance | TPRM-002 | RACI / responsibility matrix | Pending
AER-003 | Vendor inventory and tiering | Inventory | TPRM-006 | Current complete inventory | Pending
AER-004 | Sample vendor risk assessments | Risk Assessment | TPRM-007 / TPRM-008 | Completed assessments with rationale | Pending
AER-005 | Vendor risk register | Risk Register | TPRM-009 | Current risks, owners, ratings and status | Pending
AER-006 | Due diligence and security assessment evidence | Due Diligence / Security | TPRM-010 / TPRM-011 / TPRM-012 | Questionnaires, assurance and review records | Pending
AER-007 | Contracts and SLA monitoring | Contracts / SLA | TPRM-013 / TPRM-014 / TPRM-028 | Security clauses, SLA targets and performance evidence | Pending
AER-008 | Incidents and corrective actions | Incident | TPRM-015 / TPRM-027 | Incident/event and closure evidence | Pending
AER-009 | BCDR assessments/tests | BCDR | TPRM-016 / TPRM-029 | Assessment and test results | Pending
AER-010 | Risk treatment, acceptance and escalation | Risk | TPRM-017 / TPRM-024 / TPRM-025 | Actions, approvals and escalation decisions | Pending
AER-011 | Monitoring and reassessment | Monitoring | TPRM-018 / TPRM-021 / TPRM-026 | Review and monitoring records | Pending
AER-012 | Offboarding evidence | Offboarding | TPRM-019 | Exit checklist, access/data closure | Pending
AER-013 | Management dashboard and KPI/KRI reports | Management | TPRM-020 / KPI-KRI Summary | Management reporting pack | Pending
AER-014 | Evidence index and validation closure | Evidence | Evidence Index / Validation Mapping | Traceable evidence and closure records | Pending
AER-015 | Privacy / data protection assessment | Privacy | TPRM-030 | Privacy assessment and DPA review | Pending

## Auditor Interview Questions
Question ID | Topic | Sample Auditor Question | Expected Portfolio Reference
IQ-001 | Governance | Who owns the TPRM program and who can approve material vendor risk? | TPRM-001 / TPRM-002
IQ-002 | Vendor Lifecycle | How is a new vendor identified, classified and onboarded? | TPRM-005 / TPRM-006 / TPRM-010
IQ-003 | Risk Assessment | How is inherent and residual vendor risk determined? | TPRM-007 / TPRM-008 / TPRM-009
IQ-004 | Security | How do you validate vendor security claims? | TPRM-011 / TPRM-012 / TPRM-022
IQ-005 | Risk Treatment | How are vendor risks remediated and closed? | TPRM-017 / Evidence Validation
IQ-006 | Risk Acceptance | When can residual risk be accepted and who approves it? | TPRM-024
IQ-007 | Escalation | What happens when a vendor risk exceeds tolerance? | TPRM-025
IQ-008 | Monitoring | How are vendors monitored after onboarding? | TPRM-014 / TPRM-026
IQ-009 | Incidents | How are vendor incidents handled and fed back into risk? | TPRM-015 / TPRM-027 / TPRM-018
IQ-010 | Offboarding | How do you ensure access and data are closed at vendor exit? | TPRM-019
IQ-011 | Management | What KPIs/KRIs are reported to management? | TPRM-020 / KPI-KRI Summary
IQ-012 | Evidence | How can an auditor trace a control requirement to closure evidence? | Evidence Index / Validation Mapping / Cross-Document Validation