## README
TPRM-015 ¦ VENDOR INCIDENT & BREACH REGISTER | Mayekar Technologies Pvt. Ltd.
Document ID | MTPL-TPRM-015
Version | 1.0
Prepared By | Omkar Abhay Mayekar
Status | Portfolio / Simulated Evidence
Purpose | Central register for recording, assessing, escalating, investigating, remediating and closing third-party security/privacy/service incidents and breaches.
Dependency | TPRM-009 Vendor Risk Register; TPRM-013 Contract & SLA Security Register; TPRM-014 Vendor Performance & SLA Monitoring Register.
Lifecycle | Report → Triage → Classify → Contain → Investigate → Notify → Remediate → Verify → Close → Lessons Learned
Escalation | Material incidents, contractual notification events, repeated SLA breaches and high/critical impacts should be escalated according to defined governance.
Disclaimer | All incident records, timelines, impacts, root causes and actions are simulated placeholders for portfolio/learning purposes.

## Document Control
Field | Value
Document Title | Vendor Incident & Breach Register
Document ID | MTPL-TPRM-015
Version | 1.0
Organization | Mayekar Technologies Pvt. Ltd.
Prepared By | Omkar Abhay Mayekar
Reviewed By | GRC Manager — Simulated
Approved By | Management — Simulated
Effective Date | 2026-08-01
Review Cycle | Per incident and quarterly trend review
Classification | Internal / Confidential
Status | Portfolio / Simulated

## Incident Register
Incident ID | Vendor ID | Vendor Name | Contract ID | TPRM Tier | Risk Rating | Incident Date | Detected Date | Reported Date | Incident Type | Security Domain | Severity | Status | Business Impact | Data / Information Impact | Service Impact | Confidentiality Impact | Integrity Impact | Availability Impact | Initial Risk | Containment Status | Root Cause Status | Customer Notification Required | Regulatory Notification Required | Contractual Notification Required | Notification Date | Incident Owner | Vendor Contact | Internal Stakeholders | Evidence / Ticket Reference | Corrective Action | Target Closure Date | Verification Status | Closure Date | Lessons Learned | Risk Register Link | Management Escalation | Comments
INC-0001 | VND-001 | CloudSphere Infrastructure | CTR-001 | Enhanced | High |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-001-RISK | No | Simulated incident placeholder.
INC-0002 | VND-002 | Microsoft 365 Services | CTR-002 | Standard | Medium |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-002-RISK | No | Simulated incident placeholder.
INC-0003 | VND-003 | SecureVault Backup | CTR-003 | Enhanced | High |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-003-RISK | No | Simulated incident placeholder.
INC-0004 | VND-004 | TalentCore HRMS | CTR-004 | Standard | Medium |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-004-RISK | No | Simulated incident placeholder.
INC-0005 | VND-005 | PayMatrix Solutions | CTR-005 | Standard | Medium |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-005-RISK | No | Simulated incident placeholder.
INC-0006 | VND-006 | SalesFlow CRM | CTR-006 | Standard | Medium |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-006-RISK | No | Simulated incident placeholder.
INC-0007 | VND-007 | NetShield SOC Services | CTR-007 | Enhanced | High |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-007-RISK | No | Simulated incident placeholder.
INC-0008 | VND-008 | RedFort Security Testing | CTR-008 | Standard | Medium |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-008-RISK | No | Simulated incident placeholder.
INC-0009 | VND-009 | EndpointGuard Technologies | CTR-009 | Enhanced | High |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-009-RISK | No | Simulated incident placeholder.
INC-0010 | VND-010 | ConnectNet Communications | CTR-010 | Standard | Medium |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-010-RISK | No | Simulated incident placeholder.
INC-0011 | VND-011 | DataCenterOne | CTR-011 | Enhanced | High |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-011-RISK | No | Simulated incident placeholder.
INC-0012 | VND-012 | RecruitPro Services | CTR-012 | Standard | Medium |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-012-RISK | No | Simulated incident placeholder.
INC-0013 | VND-013 | FinLedger Systems | CTR-013 | Standard | Medium |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-013-RISK | No | Simulated incident placeholder.
INC-0014 | VND-014 | PayGate Services | CTR-014 | Enhanced | High |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-014-RISK | No | Simulated incident placeholder.
INC-0015 | VND-015 | ServiceDesk Pro | CTR-015 | Enhanced | High |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-015-RISK | No | Simulated incident placeholder.
INC-0016 | VND-016 | PrintSecure Solutions | CTR-016 | Basic | Low |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-016-RISK | No | Simulated incident placeholder.
INC-0017 | VND-017 | DocuSign Services | CTR-017 | Standard | Medium |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-017-RISK | No | Simulated incident placeholder.
INC-0018 | VND-018 | LegalEdge Associates | CTR-018 | Basic | Low |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-018-RISK | No | Simulated incident placeholder.
INC-0019 | VND-019 | ComplianceCheck Advisory | CTR-019 | Basic | Low |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-019-RISK | No | Simulated incident placeholder.
INC-0020 | VND-020 | SecureShred Services | CTR-020 | Basic | Low |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-020-RISK | No | Simulated incident placeholder.
INC-0021 | VND-021 | GuardForce Security | CTR-021 | Basic | Low |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-021-RISK | No | Simulated incident placeholder.
INC-0022 | VND-022 | SafeCam Systems | CTR-022 | Basic | Low |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-022-RISK | No | Simulated incident placeholder.
INC-0023 | VND-023 | OfficeNet Infrastructure | CTR-023 | Standard | Medium |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-023-RISK | No | Simulated incident placeholder.
INC-0024 | VND-024 | CodeSecure Labs | CTR-024 | Standard | Medium |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-024-RISK | No | Simulated incident placeholder.
INC-0025 | VND-025 | LearnSecure Training | CTR-025 | Basic | Low |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-025-RISK | No | Simulated incident placeholder.
INC-0026 | VND-026 | TeleSupport Services | CTR-026 | Standard | Medium |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-026-RISK | No | Simulated incident placeholder.
INC-0027 | VND-027 | MarketReach Analytics | CTR-027 | Basic | Low |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-027-RISK | No | Simulated incident placeholder.
INC-0028 | VND-028 | DevCloud Platform | CTR-028 | Standard | Medium |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-028-RISK | No | Simulated incident placeholder.
INC-0029 | VND-029 | DisasterReady DR Services | CTR-029 | Enhanced | High |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-029-RISK | No | Simulated incident placeholder.
INC-0030 | VND-030 | SecureCourier Logistics | CTR-030 | Basic | Low |  |  |  | Not Reported | Security | None | Open | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | To Be Assessed | Not Started | Not Started | Pending | Pending | Pending |  | Vendor Manager | Vendor Contact | GRC / Security / Business Owner | Pending | Investigate if incident occurs |  | Pending |  | Capture lessons learned after closure | VND-030-RISK | No | Simulated incident placeholder.

## Incident Assessment
Assessment ID | Incident ID | Vendor ID | Vendor Name | Severity | Likelihood | Impact | Risk Score | Risk Rating | C/I/A Assessment | Personal Data Involved | Regulatory Impact | Customer Impact | Financial Impact | Business Criticality | Escalation Level | Assessment Rationale | Assessor | Assessment Date
IA-0001 | INC-0001 | VND-001 | CloudSphere Infrastructure | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0002 | INC-0002 | VND-002 | Microsoft 365 Services | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0003 | INC-0003 | VND-003 | SecureVault Backup | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0004 | INC-0004 | VND-004 | TalentCore HRMS | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0005 | INC-0005 | VND-005 | PayMatrix Solutions | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0006 | INC-0006 | VND-006 | SalesFlow CRM | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0007 | INC-0007 | VND-007 | NetShield SOC Services | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0008 | INC-0008 | VND-008 | RedFort Security Testing | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0009 | INC-0009 | VND-009 | EndpointGuard Technologies | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0010 | INC-0010 | VND-010 | ConnectNet Communications | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0011 | INC-0011 | VND-011 | DataCenterOne | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0012 | INC-0012 | VND-012 | RecruitPro Services | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0013 | INC-0013 | VND-013 | FinLedger Systems | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0014 | INC-0014 | VND-014 | PayGate Services | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0015 | INC-0015 | VND-015 | ServiceDesk Pro | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0016 | INC-0016 | VND-016 | PrintSecure Solutions | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0017 | INC-0017 | VND-017 | DocuSign Services | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0018 | INC-0018 | VND-018 | LegalEdge Associates | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0019 | INC-0019 | VND-019 | ComplianceCheck Advisory | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0020 | INC-0020 | VND-020 | SecureShred Services | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0021 | INC-0021 | VND-021 | GuardForce Security | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0022 | INC-0022 | VND-022 | SafeCam Systems | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0023 | INC-0023 | VND-023 | OfficeNet Infrastructure | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0024 | INC-0024 | VND-024 | CodeSecure Labs | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0025 | INC-0025 | VND-025 | LearnSecure Training | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0026 | INC-0026 | VND-026 | TeleSupport Services | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0027 | INC-0027 | VND-027 | MarketReach Analytics | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0028 | INC-0028 | VND-028 | DevCloud Platform | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0029 | INC-0029 | VND-029 | DisasterReady DR Services | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst
IA-0030 | INC-0030 | VND-030 | SecureCourier Logistics | None | 3 | 3 | 9 | Medium | To Be Assessed | Pending | Pending | Pending | Pending | To Be Assessed | Standard | Initial assessment placeholder; update after triage. | GRC Analyst

## Notification Log
Notification ID | Incident ID | Vendor ID | Vendor Name | Notification Type | Recipient / Authority | Trigger | Required | Due Date | Sent Date | Status | Notification Reference | Approved By | Comments
NOT-0001 | INC-0001 | VND-001 | CloudSphere Infrastructure | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0002 | INC-0001 | VND-001 | CloudSphere Infrastructure | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0003 | INC-0001 | VND-001 | CloudSphere Infrastructure | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0004 | INC-0001 | VND-001 | CloudSphere Infrastructure | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0005 | INC-0001 | VND-001 | CloudSphere Infrastructure | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0006 | INC-0001 | VND-001 | CloudSphere Infrastructure | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0007 | INC-0002 | VND-002 | Microsoft 365 Services | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0008 | INC-0002 | VND-002 | Microsoft 365 Services | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0009 | INC-0002 | VND-002 | Microsoft 365 Services | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0010 | INC-0002 | VND-002 | Microsoft 365 Services | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0011 | INC-0002 | VND-002 | Microsoft 365 Services | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0012 | INC-0002 | VND-002 | Microsoft 365 Services | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0013 | INC-0003 | VND-003 | SecureVault Backup | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0014 | INC-0003 | VND-003 | SecureVault Backup | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0015 | INC-0003 | VND-003 | SecureVault Backup | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0016 | INC-0003 | VND-003 | SecureVault Backup | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0017 | INC-0003 | VND-003 | SecureVault Backup | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0018 | INC-0003 | VND-003 | SecureVault Backup | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0019 | INC-0004 | VND-004 | TalentCore HRMS | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0020 | INC-0004 | VND-004 | TalentCore HRMS | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0021 | INC-0004 | VND-004 | TalentCore HRMS | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0022 | INC-0004 | VND-004 | TalentCore HRMS | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0023 | INC-0004 | VND-004 | TalentCore HRMS | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0024 | INC-0004 | VND-004 | TalentCore HRMS | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0025 | INC-0005 | VND-005 | PayMatrix Solutions | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0026 | INC-0005 | VND-005 | PayMatrix Solutions | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0027 | INC-0005 | VND-005 | PayMatrix Solutions | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0028 | INC-0005 | VND-005 | PayMatrix Solutions | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0029 | INC-0005 | VND-005 | PayMatrix Solutions | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0030 | INC-0005 | VND-005 | PayMatrix Solutions | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0031 | INC-0006 | VND-006 | SalesFlow CRM | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0032 | INC-0006 | VND-006 | SalesFlow CRM | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0033 | INC-0006 | VND-006 | SalesFlow CRM | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0034 | INC-0006 | VND-006 | SalesFlow CRM | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0035 | INC-0006 | VND-006 | SalesFlow CRM | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0036 | INC-0006 | VND-006 | SalesFlow CRM | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0037 | INC-0007 | VND-007 | NetShield SOC Services | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0038 | INC-0007 | VND-007 | NetShield SOC Services | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0039 | INC-0007 | VND-007 | NetShield SOC Services | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0040 | INC-0007 | VND-007 | NetShield SOC Services | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0041 | INC-0007 | VND-007 | NetShield SOC Services | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0042 | INC-0007 | VND-007 | NetShield SOC Services | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0043 | INC-0008 | VND-008 | RedFort Security Testing | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0044 | INC-0008 | VND-008 | RedFort Security Testing | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0045 | INC-0008 | VND-008 | RedFort Security Testing | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0046 | INC-0008 | VND-008 | RedFort Security Testing | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0047 | INC-0008 | VND-008 | RedFort Security Testing | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0048 | INC-0008 | VND-008 | RedFort Security Testing | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0049 | INC-0009 | VND-009 | EndpointGuard Technologies | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0050 | INC-0009 | VND-009 | EndpointGuard Technologies | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0051 | INC-0009 | VND-009 | EndpointGuard Technologies | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0052 | INC-0009 | VND-009 | EndpointGuard Technologies | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0053 | INC-0009 | VND-009 | EndpointGuard Technologies | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0054 | INC-0009 | VND-009 | EndpointGuard Technologies | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0055 | INC-0010 | VND-010 | ConnectNet Communications | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0056 | INC-0010 | VND-010 | ConnectNet Communications | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0057 | INC-0010 | VND-010 | ConnectNet Communications | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0058 | INC-0010 | VND-010 | ConnectNet Communications | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0059 | INC-0010 | VND-010 | ConnectNet Communications | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0060 | INC-0010 | VND-010 | ConnectNet Communications | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0061 | INC-0011 | VND-011 | DataCenterOne | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0062 | INC-0011 | VND-011 | DataCenterOne | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0063 | INC-0011 | VND-011 | DataCenterOne | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0064 | INC-0011 | VND-011 | DataCenterOne | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0065 | INC-0011 | VND-011 | DataCenterOne | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0066 | INC-0011 | VND-011 | DataCenterOne | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0067 | INC-0012 | VND-012 | RecruitPro Services | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0068 | INC-0012 | VND-012 | RecruitPro Services | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0069 | INC-0012 | VND-012 | RecruitPro Services | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0070 | INC-0012 | VND-012 | RecruitPro Services | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0071 | INC-0012 | VND-012 | RecruitPro Services | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0072 | INC-0012 | VND-012 | RecruitPro Services | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0073 | INC-0013 | VND-013 | FinLedger Systems | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0074 | INC-0013 | VND-013 | FinLedger Systems | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0075 | INC-0013 | VND-013 | FinLedger Systems | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0076 | INC-0013 | VND-013 | FinLedger Systems | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0077 | INC-0013 | VND-013 | FinLedger Systems | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0078 | INC-0013 | VND-013 | FinLedger Systems | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0079 | INC-0014 | VND-014 | PayGate Services | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0080 | INC-0014 | VND-014 | PayGate Services | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0081 | INC-0014 | VND-014 | PayGate Services | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0082 | INC-0014 | VND-014 | PayGate Services | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0083 | INC-0014 | VND-014 | PayGate Services | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0084 | INC-0014 | VND-014 | PayGate Services | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0085 | INC-0015 | VND-015 | ServiceDesk Pro | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0086 | INC-0015 | VND-015 | ServiceDesk Pro | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0087 | INC-0015 | VND-015 | ServiceDesk Pro | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0088 | INC-0015 | VND-015 | ServiceDesk Pro | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0089 | INC-0015 | VND-015 | ServiceDesk Pro | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0090 | INC-0015 | VND-015 | ServiceDesk Pro | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0091 | INC-0016 | VND-016 | PrintSecure Solutions | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0092 | INC-0016 | VND-016 | PrintSecure Solutions | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0093 | INC-0016 | VND-016 | PrintSecure Solutions | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0094 | INC-0016 | VND-016 | PrintSecure Solutions | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0095 | INC-0016 | VND-016 | PrintSecure Solutions | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0096 | INC-0016 | VND-016 | PrintSecure Solutions | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0097 | INC-0017 | VND-017 | DocuSign Services | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0098 | INC-0017 | VND-017 | DocuSign Services | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0099 | INC-0017 | VND-017 | DocuSign Services | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0100 | INC-0017 | VND-017 | DocuSign Services | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0101 | INC-0017 | VND-017 | DocuSign Services | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0102 | INC-0017 | VND-017 | DocuSign Services | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0103 | INC-0018 | VND-018 | LegalEdge Associates | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0104 | INC-0018 | VND-018 | LegalEdge Associates | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0105 | INC-0018 | VND-018 | LegalEdge Associates | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0106 | INC-0018 | VND-018 | LegalEdge Associates | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0107 | INC-0018 | VND-018 | LegalEdge Associates | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0108 | INC-0018 | VND-018 | LegalEdge Associates | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0109 | INC-0019 | VND-019 | ComplianceCheck Advisory | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0110 | INC-0019 | VND-019 | ComplianceCheck Advisory | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0111 | INC-0019 | VND-019 | ComplianceCheck Advisory | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0112 | INC-0019 | VND-019 | ComplianceCheck Advisory | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0113 | INC-0019 | VND-019 | ComplianceCheck Advisory | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0114 | INC-0019 | VND-019 | ComplianceCheck Advisory | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0115 | INC-0020 | VND-020 | SecureShred Services | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0116 | INC-0020 | VND-020 | SecureShred Services | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0117 | INC-0020 | VND-020 | SecureShred Services | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0118 | INC-0020 | VND-020 | SecureShred Services | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0119 | INC-0020 | VND-020 | SecureShred Services | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0120 | INC-0020 | VND-020 | SecureShred Services | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0121 | INC-0021 | VND-021 | GuardForce Security | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0122 | INC-0021 | VND-021 | GuardForce Security | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0123 | INC-0021 | VND-021 | GuardForce Security | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0124 | INC-0021 | VND-021 | GuardForce Security | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0125 | INC-0021 | VND-021 | GuardForce Security | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0126 | INC-0021 | VND-021 | GuardForce Security | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0127 | INC-0022 | VND-022 | SafeCam Systems | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0128 | INC-0022 | VND-022 | SafeCam Systems | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0129 | INC-0022 | VND-022 | SafeCam Systems | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0130 | INC-0022 | VND-022 | SafeCam Systems | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0131 | INC-0022 | VND-022 | SafeCam Systems | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0132 | INC-0022 | VND-022 | SafeCam Systems | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0133 | INC-0023 | VND-023 | OfficeNet Infrastructure | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0134 | INC-0023 | VND-023 | OfficeNet Infrastructure | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0135 | INC-0023 | VND-023 | OfficeNet Infrastructure | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0136 | INC-0023 | VND-023 | OfficeNet Infrastructure | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0137 | INC-0023 | VND-023 | OfficeNet Infrastructure | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0138 | INC-0023 | VND-023 | OfficeNet Infrastructure | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0139 | INC-0024 | VND-024 | CodeSecure Labs | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0140 | INC-0024 | VND-024 | CodeSecure Labs | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0141 | INC-0024 | VND-024 | CodeSecure Labs | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0142 | INC-0024 | VND-024 | CodeSecure Labs | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0143 | INC-0024 | VND-024 | CodeSecure Labs | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0144 | INC-0024 | VND-024 | CodeSecure Labs | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0145 | INC-0025 | VND-025 | LearnSecure Training | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0146 | INC-0025 | VND-025 | LearnSecure Training | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0147 | INC-0025 | VND-025 | LearnSecure Training | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0148 | INC-0025 | VND-025 | LearnSecure Training | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0149 | INC-0025 | VND-025 | LearnSecure Training | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0150 | INC-0025 | VND-025 | LearnSecure Training | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0151 | INC-0026 | VND-026 | TeleSupport Services | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0152 | INC-0026 | VND-026 | TeleSupport Services | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0153 | INC-0026 | VND-026 | TeleSupport Services | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0154 | INC-0026 | VND-026 | TeleSupport Services | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0155 | INC-0026 | VND-026 | TeleSupport Services | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0156 | INC-0026 | VND-026 | TeleSupport Services | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0157 | INC-0027 | VND-027 | MarketReach Analytics | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0158 | INC-0027 | VND-027 | MarketReach Analytics | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0159 | INC-0027 | VND-027 | MarketReach Analytics | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0160 | INC-0027 | VND-027 | MarketReach Analytics | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0161 | INC-0027 | VND-027 | MarketReach Analytics | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0162 | INC-0027 | VND-027 | MarketReach Analytics | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0163 | INC-0028 | VND-028 | DevCloud Platform | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0164 | INC-0028 | VND-028 | DevCloud Platform | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0165 | INC-0028 | VND-028 | DevCloud Platform | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0166 | INC-0028 | VND-028 | DevCloud Platform | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0167 | INC-0028 | VND-028 | DevCloud Platform | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0168 | INC-0028 | VND-028 | DevCloud Platform | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0169 | INC-0029 | VND-029 | DisasterReady DR Services | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0170 | INC-0029 | VND-029 | DisasterReady DR Services | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0171 | INC-0029 | VND-029 | DisasterReady DR Services | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0172 | INC-0029 | VND-029 | DisasterReady DR Services | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0173 | INC-0029 | VND-029 | DisasterReady DR Services | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0174 | INC-0029 | VND-029 | DisasterReady DR Services | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0175 | INC-0030 | VND-030 | SecureCourier Logistics | Internal Management | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0176 | INC-0030 | VND-030 | SecureCourier Logistics | Customer | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0177 | INC-0030 | VND-030 | SecureCourier Logistics | Contractual | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0178 | INC-0030 | VND-030 | SecureCourier Logistics | Regulatory | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0179 | INC-0030 | VND-030 | SecureCourier Logistics | Data Protection Authority | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record
NOT-0180 | INC-0030 | VND-030 | SecureCourier Logistics | Law Enforcement (if applicable) | To Be Determined | Incident assessment | Pending |  |  | Pending |  | GRC Manager | Simulated notification record

## Corrective Action Tracker
Action ID | Incident ID | Vendor ID | Vendor Name | Severity | Corrective Action | Action Owner | Target Date | Status | Root Cause Addressed | Verification Evidence | Verification Status | Closure Date | Risk Treatment Link | Comments
ACT-INC-001 | INC-0001 | VND-001 | CloudSphere Infrastructure | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-002 | INC-0002 | VND-002 | Microsoft 365 Services | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-003 | INC-0003 | VND-003 | SecureVault Backup | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-004 | INC-0004 | VND-004 | TalentCore HRMS | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-005 | INC-0005 | VND-005 | PayMatrix Solutions | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-006 | INC-0006 | VND-006 | SalesFlow CRM | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-007 | INC-0007 | VND-007 | NetShield SOC Services | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-008 | INC-0008 | VND-008 | RedFort Security Testing | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-009 | INC-0009 | VND-009 | EndpointGuard Technologies | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-010 | INC-0010 | VND-010 | ConnectNet Communications | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-011 | INC-0011 | VND-011 | DataCenterOne | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-012 | INC-0012 | VND-012 | RecruitPro Services | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-013 | INC-0013 | VND-013 | FinLedger Systems | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-014 | INC-0014 | VND-014 | PayGate Services | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-015 | INC-0015 | VND-015 | ServiceDesk Pro | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-016 | INC-0016 | VND-016 | PrintSecure Solutions | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-017 | INC-0017 | VND-017 | DocuSign Services | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-018 | INC-0018 | VND-018 | LegalEdge Associates | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-019 | INC-0019 | VND-019 | ComplianceCheck Advisory | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-020 | INC-0020 | VND-020 | SecureShred Services | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-021 | INC-0021 | VND-021 | GuardForce Security | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-022 | INC-0022 | VND-022 | SafeCam Systems | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-023 | INC-0023 | VND-023 | OfficeNet Infrastructure | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-024 | INC-0024 | VND-024 | CodeSecure Labs | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-025 | INC-0025 | VND-025 | LearnSecure Training | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-026 | INC-0026 | VND-026 | TeleSupport Services | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-027 | INC-0027 | VND-027 | MarketReach Analytics | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-028 | INC-0028 | VND-028 | DevCloud Platform | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-029 | INC-0029 | VND-029 | DisasterReady DR Services | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder
ACT-INC-030 | INC-0030 | VND-030 | SecureCourier Logistics | None | To be defined after incident investigation. | Vendor Manager |  | Open | Pending | Attach evidence after remediation. | Pending |  |  | Simulated action placeholder

## Executive Summary
Metric | Value | Management Interpretation | Severity | Count
Vendor Population | 30 | Vendors in current incident management scope | None | 30
Incident Records | 30 | One monitoring placeholder per vendor | Low | 0
Critical Incidents | 0 | Immediate management escalation | Medium | 0
High Incidents | 0 | Priority investigation and treatment | High | 0
Open Incidents | 30 | Current incident backlog | Critical | 0
Security/Data Breach Records | 0 | Requires security response and notification assessment
Notification Records | 180 | Notification tracking population
Corrective Action Records | 30 | Initial remediation tracking population
Management Escalations | 0 | Escalated incident population

## Incident Trend Log
Period | Total Incidents | Security Incidents | Data Breaches | Privacy Incidents | Service Outages | SLA Breaches | High/Critical | Open | Closed | Trend / Management Comment
2026-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update monthly using Incident Register and management review.
2026-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update monthly using Incident Register and management review.
2026-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update monthly using Incident Register and management review.
2026-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update monthly using Incident Register and management review.
2026-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update monthly using Incident Register and management review.
2027-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update monthly using Incident Register and management review.
2027-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update monthly using Incident Register and management review.
2027-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update monthly using Incident Register and management review.
2027-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update monthly using Incident Register and management review.
2027-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update monthly using Incident Register and management review.
2027-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update monthly using Incident Register and management review.
2027-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update monthly using Incident Register and management review.

## Incident Methodology
Area | Guidance | Rule
Triage | Quickly determine incident type, scope, severity and response needs | Record initial facts and update as investigation progresses
Severity | Assess confidentiality, integrity, availability, privacy, customer, financial and regulatory impact | Use defined severity/risk model
Containment | Limit ongoing harm or exposure | Document containment action and owner
Notification | Determine internal, customer, contractual and regulatory notification obligations | Record trigger, due date, approval and evidence
Investigation | Determine root cause and contributing factors | Maintain evidence and investigation trail
Remediation | Correct control/service weakness | Track action to verified closure
Lessons Learned | Identify systemic improvements | Feed outcomes into TPRM risk, controls and vendor oversight
Escalation | Escalate material/repeated incidents | Link to risk register and management governance

## Data Dictionary
Field | Purpose
Incident ID | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Vendor ID | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Vendor Name | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Contract ID | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
TPRM Tier | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Risk Rating | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Incident Date | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Detected Date | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Reported Date | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Incident Type | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Security Domain | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Severity | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Status | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Business Impact | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Data / Information Impact | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Service Impact | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Confidentiality Impact | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Integrity Impact | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Availability Impact | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Initial Risk | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Containment Status | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Root Cause Status | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Customer Notification Required | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Regulatory Notification Required | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Contractual Notification Required | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Notification Date | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Incident Owner | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Vendor Contact | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Internal Stakeholders | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Evidence / Ticket Reference | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Corrective Action | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Target Closure Date | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Verification Status | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Closure Date | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Lessons Learned | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Risk Register Link | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Management Escalation | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.
Comments | Field used to record, assess, notify, investigate, remediate, escalate and close third-party incidents/breaches.